## History of changes
|  | ESTIMATION | No: BM-2-901-22
Version: 1.5
Issue Date: 10/03/2026
SUN ASTERISK VIETNAM CO., LTD |  |  | ISO/IEC 27001:2022 & ISO 9001:2015
HISTORY OF CHANGES
No | Change Item | Description of changes | Change Date | Version
1 |  | Update format | 2021-05-04
2 | Sheet Note-Coeficient | Change Working hours in a day from 8 hour to 7 hour | 14/04/2023
3 | Techical Suggestion | Add new sheet about Technical Suggestion | 28/06/2023
4 | Sheet 00_Summary | Update nội dung mục Assumptions | 26/11/2024
5 | Security Requirement | Update thêm mục Security Requirement ở sheet 00_Summary Add new sheet about Security Requirement & Security Requirement (Recommendation) | 2024-06-12
6 | Sheet Summary | Thay đổi Project Role theo thay đổi cơ cấu mới của tổ chức - PSM -> Project Leader | 23/12/2024
7 | Remove | Remove 2 sheet: 04_Security Requirement và 04_Security Requirement (Recommendation) | 2025-02-06
8 | Add new | Bổ sung sheet 04_Infrastructure for AWS dành cho hoạt động estimation liên quan đến AWS | 21/11/2025
9 | 00_Summary | Bổ sung mục III. Documents List tại sheet 00_Summary | 06/02/2026 | v1.4
10 | 00_Summary | Tại sheet 00_Summary: - Đổi tên mục III. Documents List thành mục IV. Documents List - Thêm mới mục III. Deliveriable List: liệt kê danh sách các output cần bàn giao cho Khách hàng dựa trên sự thống nhất giữa Sun* và Khách hàng. | 10/03/2026 | v1.5
11 | Add new | Thêm mới sheet 05_Resource Plan: nhằm cung cấp cái nhìn tổng thể về kế hoạch phân bổ nguồn lực theo từng vai trò và theo từng giai đoạn/thời gian phát triển của dự án. | 10/03/2026 | v1.5

## Technical Suggestion
| ESTIMATION |  | No: BM-2-901-22
Version: 1.5
Issue Date: 10/03/2026
SUN ASTERISK VIETNAM CO., LTD |  |  | ISO/IEC 27001:2022 & ISO 9001:2015
Reference document tại đây
■ Development strategy: |  | MVP / POC
■ Type of service: |  | Web
■ Programming language:
■ Framework:
■ Server or serverless: |  | Server
■ Infrastructure diagram: |  | Link to diagram
■ Infrastructure cost: |  | Link to AWS/GCP... calculator
■ Use IaC (infrastructure as code) tool to build environment: |  | Terraform
■ Web rendering method: |  | Server Side Redering (SSR)
■ Use admin template tool: |  | LaravelAdmin
■ Apply performance test: |  | Yes
■ Suggest services for specific modules/functions:

## 00_Summary
|  |  | ESTIMATION | [5 empty] | No: BM-2-901-22
Version: 1.5
Issue Date: 10/03/2026
SUN ASTERISK VIETNAM CO., LTD | [8 empty] | ISO/IEC 27001:2022 & ISO 9001:2015
I. Effort
| No. | Role | Total Effort (MM) | Note
| 1 | Backend
| 2 | Frontend
| 3 | Native App
| 4 | QA
| 5 | AI
| 6 | Infrastructure
| 7 | Design UI/UX
| 8 | Specification
Total
II. Scope & Assumptions
1. In Scope
The scope for estimate does include the following items:
| # | Item | Description | Note
1
2
2. Out of Scope
The estimation does not include the following items:
| # | Item | Description | Note
1
2
3. Assumptions
| 3-1. Overall Assumptions | [7 empty] | → Japanese Translation 日本語訳（自動翻訳）
| # | Item |  | Applicable degree | Assumptions |  | Reason for not applicable |  | # | アイテム |  | 該当する学位 | 前提条件 | 該当しない理由
| 1 | Accuracy of this estimation |  | Super Rough |  |  |  |  | 1 | 見積もりの精度 |  | Super Rough
| 2 | Roles and expected outputs of each role (What tasks will each role be responsible for, and what will they output?) Ref: Responsibility of each role: [JP] Onboarding for JPPM | PSM | TRUE |  |  |  |  | 2 | 各役割の役割と期待される成果 （各役割はどのようなタスクを担当し、どのような成果を出すのか？） 参考：各役割の責任：[JP] Onboarding for JPPM | PSM | TRUE
|  |  | BrSE | TRUE | [6 empty] | BrSE | TRUE
|  |  | Communicator | TRUE | [6 empty] | Communicator | TRUE
| 3 | Roles and expected output from JP members (What are you expecting to get from JP side?) |  | TRUE |  |  |  |  | 3 | JPメンバーの役割と期待される成果 （JP側から何を期待していますか？） |  | TRUE
| 4 | Schedule and expected inputs and outputs at each milestone (When and what will be output during the project period? When are dependent inputs expected to be completed/received?) Example: timeline for receiving existing database structure from customer and timeline for starting development |  | Must have |  |  |  |  | 4 | 各マイルストーンにおけるスケジュールと予想される入出力 (プロジェクト期間中にいつ、どのような出力が行われるか？依存する入出力はいつ完了／受領される予定か？) 例: 顧客から既存のデータベース構造を受け取るまでのタイムラインと開発開始までのタイムライン |  | Must have
| 5 | Number of screens |  | Must have |  |  |  |  | 5 | スクリーン数 |  | Must have
| 6 | Number of APIs per screen |  | TRUE |  |  |  |  | 6 | 画面あたりのAPI数 |  | TRUE
| 7 | Interfaces |  | TRUE |  |  |  |  | 7 | インターフェース |  | TRUE
| 8 | Forms ("Cho-hyo" in Japanese) |  | TRUE |  |  |  |  | 8 | 帳簿（ちょうひょう） |  | TRUE
| 9 | System scale (How do you envision the number of users and infrastructure configuration? *If specified by the customer, attach a link to the customer request.) |  | TRUE |  |  |  |  | 9 | システム規模 （ユーザー数とインフラ構成はどのように想定されていますか？ *お客様からご指定がある場合は、お客様リクエストへのリンクを添付してください。） |  | TRUE
| 10 | Non-functional requirements (What do you envision for SLA and security requirements? *If specified by the customer, attach a link to the customer request.) |  | FALSE |  |  |  |  | 10 | 非機能要件 (SLAとセキュリティ要件についてはどのようなことを想定していますか？ *お客様からご指定がある場合は、お客様からのリクエストへのリンクを添付してください。) |  | FALSE
| 11 | Buffer rate (%) and its breakdown (Buffer for risk, such as change request, bugs and issue solving, technical difficulty only) |  | Must have |  |  |  |  | 11 | バッファ率（%）とその内訳 （変更要求、バグや問題解決、技術的困難などのリスクに対するバッファのみ） |  | Must have
| 3-2. Detail Assumptions per each role | [7 empty] | → Japanese Translation 日本語訳（自動翻訳）
| Role | Item |  | Applicable degree | Assumptions |  | Reason for not applicable |  | 役割 | アイテム |  | 該当する学位 | 前提条件 | 該当しない理由
| Backend | Develop new system or Develop in existing System? |  | Must have |  |  |  |  | Backend | 新規システムを開発するか、既存システム内で開発するか？ |  | Must have
|  | Architecture (microservices, monolithic, multitenant) |  | TRUE | [5 empty] | アーキテクチャ（マイクロサービス、モノリシック、マルチテナント） |  | TRUE
|  | Scope of work | Unit Test | TRUE | [5 empty] | 作業範囲 | 単体テスト | TRUE
|  |  | Provide system Design | TRUE | [6 empty] | システム設計を提供する | TRUE
|  |  | Provide API Design | TRUE | [6 empty] | API設計を提供する | TRUE
|  |  | Provide DB Design | TRUE | [6 empty] | データベース設計を提供する | TRUE
|  |  | Integrate CI/CD | TRUE | [6 empty] | CI/CDを統合する | TRUE
|  |  | Intergrate third parties services | TRUE | [6 empty] | サードパーティサービスを統合する | TRUE
|  |  | Develop payment related functions | TRUE | [6 empty] | 支払い関連機能の開発 | TRUE
|  |  | Migrate data from old system | TRUE | [6 empty] | 古いシステムからデータを移行する | TRUE
|  |  | Production Deployment | TRUE | [6 empty] | 本番環境への展開 | TRUE
|  | Other assumed risks and assumptions |  | Must have | [5 empty] | その他の想定リスクおよび前提条件 |  | Must have
|  | Buffer rate (%) |  | Must have | [5 empty] | バッファ率（％） |  | Must have
| Frontend | Develop new system or Develop in existing System? |  | Must have |  |  |  |  | Frontend | 新規システムを開発するか、既存システム内で開発するか？ |  | Must have
|  | Architectural assumptions - Frameworks and libraries used - Whether SSR or CSR is applied |  | TRUE | [5 empty] | アーキテクチャ上の前提条件 - 使用するフレームワークとライブラリ - SSRまたはCSRの適用の有無 |  | TRUE
|  | Browser and versions (Chrome, Safari, IE etc) |  | TRUE | [5 empty] | ブラウザとバージョン（Chrome、Safari、IEなど） |  | TRUE
|  | Scope of work | Responsive design | TRUE | [5 empty] | 作業範囲 | レスポンシブデザイン | TRUE
|  |  | State management | TRUE | [6 empty] | 国家管理 | TRUE
|  |  | Automated testing | TRUE | [6 empty] | 自動テスト | TRUE
|  |  | Unit test | TRUE | [6 empty] | 単体テスト | TRUE
|  |  | SEO(Google Analytics, OGP tag, SSR) | TRUE | [6 empty] | SEO（Google Analytics、OGPタグ、SSR） | TRUE
|  |  | Intergrate third parties services | TRUE | [6 empty] | サードパーティサービスを統合する | TRUE
|  |  | Integrate CI/CD | TRUE | [6 empty] | CI/CDを統合する | TRUE
|  |  | Production Deployment | TRUE | [6 empty] | 本番環境への展開 | TRUE
|  | Other assumed risks and assumptions |  | Must have | [5 empty] | その他の想定リスクおよび前提条件 |  | Must have
|  | Buffer rate (%) |  | Must have | [5 empty] | バッファ率（％） |  | Must have
| Mobile | Develop new system or Develop in existing System? |  | Must have |  |  |  |  | Mobile | 新規システムを開発するか、既存システム内で開発するか？ |  | Must have
|  | OS and versions (iOS, Android) |  | TRUE | [5 empty] | OSとバージョン（iOS、Android） |  | TRUE
|  | Scope of work | Unit test | TRUE | [5 empty] | 作業範囲 | 単体テスト | TRUE
|  |  | Intergrate third parties services | TRUE | [6 empty] | サードパーティサービスを統合する | TRUE
|  |  | Integrate CI/CD | TRUE | [6 empty] | CI/CDを統合する | TRUE
|  |  | Play store / App store publish | TRUE | [6 empty] | Playストア/Appストアで公開 | TRUE
|  | Other assumed risks and assumptions |  | Must have | [5 empty] | その他の想定リスクおよび前提条件 |  | Must have
|  | Buffer rate (%) |  | Must have | [5 empty] | バッファ率（％） |  | Must have
| QA | Productivity | Test case creation | Must have | [ ] case/1 man-day |  |  |  | QA | 生産性 | テストケースの作成 | Must have | [ ] 症例/1人日
|  |  | Test execution and bug identification | Must have | [ ] case/1 man-day | [5 empty] | テスト実行とバグの特定 | Must have | [ ] 症例/1人日
|  |  | Final inspection effort in total man-hours | Must have | [ ] % | [5 empty] | 最終検査にかかる総工数 | Must have | [ ] %
|  |  | Expected bug occurrence rate | Must have | [ ] % | [5 empty] | 予想されるバグ発生率 | Must have | [ ] %
|  | Testing scope | Function test | TRUE | [5 empty] | テスト範囲 | 機能テスト | TRUE
|  |  | Integration test | TRUE | [6 empty] | 統合テスト | TRUE
|  |  | E2E test (Screen, API end point) | TRUE | [6 empty] | エンドツーエンドテスト（画面、APIエンドポイント） | TRUE
|  |  | Regression test | TRUE | [6 empty] | リグレッションテスト | TRUE
|  |  | Other test | TRUE | [6 empty] | その他のテスト | TRUE
|  |  | Environments to be tested and range of test cases covered for each environment | Must have | [6 empty] | テスト対象環境と、各環境でカバーされるテストケースの範囲 | Must have
|  | Buffer rate (%) |  | Must have | [5 empty] | バッファ率（％） |  | Must have
| AI | Data flow in the AI scope |  | TRUE |  |  |  |  | AI | AI スコープ内のデータ フロー |  | TRUE
|  | Architecture in the AI ​​scope |  | TRUE | [5 empty] | AIの範囲におけるアーキテクチャ |  | TRUE
|  | AI models and AI services |  | TRUE | [5 empty] | AIモデルとAIサービス |  | TRUE
|  | Estimated cost of AI infrastructure (at the time of development and operation after release) |  | TRUE | [5 empty] | AIインフラの概算費用（開発時、リリース後の運用時） |  | TRUE
|  | Possibility of training (tuning) of AI models |  | TRUE | [5 empty] | AIモデルのトレーニング（チューニング）が可能 |  | TRUE
|  | Number of data required when training (tuning) an AI model |  | TRUE | [5 empty] | AIモデルのトレーニング（チューニング）時に必要なデータ数 |  | TRUE
|  | Prerequisites for implementing AI models and degree of difficulty in realizing them |  | TRUE | [5 empty] | AIモデル導入の前提条件と実現難易度 |  | TRUE
|  | Other assumed risks and assumptions (if not available, write “none”) |  | Must have | [5 empty] | その他の想定されるリスクと仮定 (利用できない場合は「なし」と記入してください) |  | Must have
|  | Buffer value (%) |  | Must have | [5 empty] | バッファ値（％） |  | Must have
| Infrastructure | Building environment; Dev, Stag, UAT, Prod etc |  | Must have |  |  |  |  | Infrastructure | 構築環境；開発、ステージング、UAT、本番など |  | Must have
|  | Cloud service selection and architecture |  | TRUE | [5 empty] | クラウドサービスの選択とアーキテクチャ |  | TRUE
|  | Selection and management of containers and virtual machines (VM) |  | TRUE | [5 empty] | コンテナおよび仮想マシン（VM）の選択と管理 |  | TRUE
|  | Database |  | TRUE | [5 empty] | データベース |  | TRUE
|  | Network design and security measures |  | TRUE | [5 empty] | ネットワーク設計とセキュリティ対策 |  | TRUE
|  | Caching (CDN, redis, In-memory caching system, etc.) |  | TRUE | [5 empty] | キャッシング（CDN、Redis、インメモリキャッシングシステムなど） |  | TRUE
|  | CI/CD |  | TRUE | [5 empty] | CI/CD |  | TRUE
|  | Monitoring and alerting |  | TRUE | [5 empty] | 監視と警告 |  | TRUE
|  | Backup and recovery strategy |  | TRUE | [5 empty] | バックアップと復旧戦略 |  | TRUE
|  | Performance testing and load testing |  | TRUE | [5 empty] | パフォーマンス テストと負荷テスト |  | TRUE
|  | Other assumptions for non-functional requirements (availability, performance/scalability, operational maintainability, portability, things to be done to ensure security etc) |  | TRUE | [5 empty] | 非機能要件に関するその他の前提条件（可用性、パフォーマンス／拡張性、運用保守性、移植性、セキュリティ確保のために実施すべき事項など） |  | TRUE
|  | Production Deployment and Maintenance |  | TRUE | [5 empty] | 本番環境への展開と保守 |  | TRUE
|  | Other assumed risks and assumptions |  | Must have | [5 empty] | その他の想定リスクおよび前提条件 |  | Must have
|  | Buffer rate (%) |  | Must have | [5 empty] | バッファ率（％） |  | Must have
| Design | Scope of work | Wireframe | TRUE |  |  |  |  | Design | 作業範囲 | ワイヤーフレーム | TRUE
|  |  | Mockup | TRUE | [6 empty] | モックアップ | TRUE
|  |  | Other | TRUE | [6 empty] | 他の | TRUE
|  | Buffer rate (%) |  | Must have | [5 empty] | バッファ率（％） |  | Must have
III. Deliveriables List
| No. | Deliveriable Item | Delivery Schedule |  | Language | Note
| 1 | Functional Requirement 機能一覧 | End of Requirement Definition |  | JP
| 2 | Spec Basic design 基本設計書（簡易版） | End of Basic Design |  | EN
| 3 | Source Code | After UAT |  | N/A
| 4 | .......
| 5 | ........
IV. Documents List
| No. | Document Name | PIC | Language | Tool/ Doc Type |  | Output Sample | Note
| 1 | Functional Requirement 機能一覧 | SJP (PM) | Japanese | Excel
| 2 | Non functional Requirement list 非機能要件定義書 | SJP(JP Engineer) | Japanese | Excel
| 3 | As is business flow 既存業務フロー | SJP (PM) | Japanese | Docs
| 4 | To be business flow 新規の想定業務フロー | SJP (PM) | Japanese | Excel
| 5 | Screen List 画面一覧 | SJP (PM) | Japanese | Docs
| 6 | Screen flow 画面遷移図 | SJP (Designer) | Japanese | Figma
| 6 | Wireframe ワイヤーフレーム | SJP (Designer) | Japanese | Figma
| 6 | Design concept デザインコンセプト | SJP (Designer) | Japanese | Miro
| 6 | Prototype プロトタイプ | SJP (Designer) | Japanese | Protopie
| 7 | Design UI/UX デザインカンプ | SJP (Designer) | Japanese | Figma
| 8 | システム構成図 | SJP(JP Engineer) | Japanese | Excel
| 9 | ERD diagram ERD図 | SVN | English & Japanese (Tool) | Excel |  | https://sal.vn/JfUEt9 | Server見積に含まれている 開発フェーズの成果物
| 10 | Database design データベース設計 | SVN | English & Japanese (Tool) | Excel |  | https://sal.vn/Qiljbw | Server見積に含まれている 開発フェーズの成果物
| 11 | System design システム設計 | SVN | English & Japanese (Tool) | Docs |  |  | Server見積に含まれている 開発フェーズの成果物
| 12 | Spec Basic design 基本設計書（簡易版） | SJP | English & Japanese (Tool) | Docs |  |  | Spec design見積に含まれている 開発フェーズの成果物
| 13 | Screen Specification 画面仕様書 | SVN / SJP (Designer) | English & Japanese (Tool) | MoMorph |  | https://sal.vn/zzeRzq | Spec design見積に含まれている 開発フェーズの成果物
| 14 | Test Plan テスト計画書 | SVN | English & Japanese (Tool) | Docs
| 15 | Test case & Result テスト仕様書 | SVN | English & Japanese (Tool) | Excel |  | https://sal.vn/tFxiD8 | QA見積に含まれている 開発フェーズの成果物
| 16 | Infra structure インフラ構成図 | SVN | English & Japanese (Tool) | Slide |  |  | Infra見積に含まれている 開発フェーズの成果物
| 17 | 外部I/F定義書 | SJP(JP Engineerr) & SVN | Japanese & English | Excel |  |  | EDI,CSV等の連携仕様
| 18 | Sequence Diagram シーケンス図 | SVN | English & Japanese (Tool) | Excel
| 19 | Migration Plan 移行計画書 | SVN | English & Japanese (Tool) | Excel
| 20 | Release Plan リリース計画書 | SVN | English & Japanese (Tool) | Docs
| 21 | Operations Design Document and Manual 運用設計書及びマニュアル | SVN | English & Japanese (Tool) | Docs

## 01_Server
|  |  | ESTIMATION | [5 empty] | No: BM-2-901-22
Version: 1.5
Issue Date: 10/03/2026
SUN ASTERISK VIETNAM CO., LTD | [8 empty] | ISO/IEC 27001:2022 & ISO 9001:2015
Server
Total (MM) |  |  |  | 8.06 | 2.418 | 5.642 | 0.585 | 0.1755 | 0.4095 | 0.585
No | Category | Screen・Feature | Task | Effort（Man-days） | [6 empty] | Note
|  |  |  | Backend |  |  | Frontend |  |  | DesignUX/UI
|  |  |  | Implement | FixBug | Unit Test | Implement | FixBug | Unit Test
1 | 共通 | ログイン・ログアウト |  | 2 | 0.6 | 1.4 | 1 | 0.3 | 0.7 | 1
2 |  | WF再発行 メール送信 |  | 1.5 | 0.45 | 1.05 | 1 | 0.3 | 0.7 | 1
3 |  | WF再設定 |  | 1.5 | 0.45 | 1.05 | 1 | 0.3 | 0.7 | 1
4 | Contractor | 契約者情報登録 |  | 3 | 0.9 | 2.1 | 1 | 0.3 | 0.7 | 1
5 |  | 契約情報登録 |  | 3 | 0.9 | 2.1 | 1 | 0.3 | 0.7 | 1
6 |  | 決済情報登録 |  | 3 | 0.9 | 2.1 | 0 | 0 | 0 | 0
7 |  | トップ |  | 2 | 0.6 | 1.4 | 0 | 0 | 0 | 0
8 |  | Manager一覧 |  | 3 | 0.9 | 2.1 | 0 | 0 | 0 | 0
9 |  | Manager登録・編集・削除 |  | 3 | 0.9 | 2.1 | 0 | 0 | 0 | 0
10 | Manager | アカウント登録 |  | 3 | 0.9 | 2.1 | 0 | 0 | 0 | 0
11 |  | Manager一覧 |  | 2 | 0.6 | 1.4 | 0 | 0 | 0 | 0
12 |  | Manager登録・編集・削除 |  | 3 | 0.9 | 2.1 | 0 | 0 | 0 | 0
13 |  | グループ一覧 |  | 2 | 0.6 | 1.4 | 0 | 0 | 0 | 0
14 |  | グループ登録・編集・削除 |  | 3 | 0.9 | 2.1 | 0 | 0 | 0 | 0
15 |  | Managerカレンダー |  | 5 | 1.5 | 3.5 | 0 | 0 | 0 | 0
16 |  | トレーニング登録・編集 |  | 3 | 0.9 | 2.1 | 0 | 0 | 0 | 0
17 |  | イベント登録・編集 |  | 3 | 0.9 | 2.1 | 0 | 0 | 0 | 0
18 |  | トレーニングアイテム一覧 |  | 2 | 0.6 | 1.4 | 0 | 0 | 0 | 0
19 |  | トレーニングアイテム登録・編集・削除 |  | 2 | 0.6 | 1.4 | 0 | 0 | 0 | 0
20 |  | Athlete一覧 |  | 2 | 0.6 | 1.4 | 0 | 0 | 0 | 0
21 |  | Athlete登録・削除 |  | 3 | 0.9 | 2.1 | 0 | 0 | 0 | 0
22 |  | 各種情報推移 |  | 7 | 2.1 | 4.9 | 0 | 0 | 0 | 0
23 |  | 目標登録 |  | 3 | 0.9 | 2.1 | 0 | 0 | 0 | 0
24 |  | パフォーマンス登録 |  | 2 | 0.6 | 1.4 | 0 | 0 | 0 | 0
25 |  | 推奨摂取栄養価表示・ダウンロード |  | 5 | 1.5 | 3.5 | 0 | 0 | 0 | 0
26 |  | アスリートカレンダー |  | 5 | 1.5 | 3.5 | 0 | 0 | 0 | 0
27 |  | グループメッセージ |  | 7 | 2.1 | 4.9 | 0 | 0 | 0 | 0
34 |  | 退会 |  | 1 | 0.3 | 0.7 | 0 | 0 | 0 | 0
23 | Admin | 加盟コントラクター承認 |  | 3 | 0.9 | 2.1 | 1 | 0.3 | 0.7 | 1
24 |  | 競技団体告知登録 |  | 2 | 0.6 | 1.4 | 1 | 0.3 | 0.7 | 1
25 |  | 問い合わせ対応 |  | 6.5 | 1.95 | 4.55 | 1 | 0.3 | 0.7 | 1
26 |  | ユーザー情報管理 |  | 4.5 | 1.35 | 3.15 | 1 | 0.3 | 0.7 | 1
27 |  | 契約情報管理 |  | 4.5 | 1.35 | 3.15 | 0 | 0 | 0 | 0
28 |  | 請求情報管理 |  | 3.5 | 1.05 | 2.45 | 0 | 0 | 0 | 0
29 |  | お知らせ登録 |  | 3.5 | 1.05 | 2.45 | 0 | 0 | 0 | 0
30 |  | マスタデータ登録 |  | 3.5 | 1.05 | 2.45 | 0 | 0 | 0 | 0
31 |  | システムメンテナンス |  | 3.5 | 1.05 | 2.45 | 0 | 0 | 0 | 0
32 |  | システムバックアップ |  | 3.5 | 1.05 | 2.45 | 0 | 0 | 0 | 0
33 |  | ログイン・ログアウト |  | 1 | 0.3 | 0.7 | 0 | 0 | 0 | 0

## 02_Native App
|  |  | ESTIMATION | [6 empty] | No: BM-2-901-22
Version: 1.5
Issue Date: 10/03/2026
SUN ASTERISK VIETNAM CO., LTD | [9 empty] | ISO/IEC 27001:2022 & ISO 9001:2015
Native(iOS/Android)
Total (MM) |  |  |  | 5.785 | 1.7355 | 4.0495 | 5.85 | 1.755 | 4.095 | 2.6
No | Category | Screen・Feature | Task | Effort（Man-days） | [6 empty] | Note
|  |  |  | iOS |  |  | Android |  |  | DesignUX/UI
|  |  |  | Implement | FixBug | Unit Test | Implement | FixBug | Unit Test
1 | アカウント | A0001 ログイン |  | 2 | 0.6 | 1.4 | 3 | 0.9 | 2.1 | 1
2 |  | A0005 アカウント新規登録 |  | 4 | 1.2 | 2.8 | 4 | 1.2 | 2.8 | 2
3 |  | A0002 PW再発行 |  | 1 | 0.3 | 0.7 | 1 | 0.3 | 0.7 | 0
4 |  | A0003 PW再設定 |  | 1 | 0.3 | 0.7 | 1 | 0.3 | 0.7 | 0
5 | 情報推移 | A0011 各種情報推移 |  | 14 | 4.2 | 9.8 | 14 | 4.2 | 9.8 | 0
6 | メニュー | A0009 メニュー検索 (popup) |  | 2 | 0.6 | 1.4 | 2 | 0.6 | 1.4 | 5
7 |  | A0009 メニュー登録・修正 |  | 3 | 0.9 | 2.1 | 3 | 0.9 | 2.1 | 0
9 | カレンダー | A0012 アスリートカレンダー |  | 9 | 2.7 | 6.3 | 9 | 2.7 | 6.3 | 0
10 |  | A0007トレーニング状況登録 |  | 4 | 1.2 | 2.8 | 4 | 1.2 | 2.8 | 0
11 |  | A0010 栄養パランス |  | 9 | 2.7 | 6.3 | 9 | 2.7 | 6.3 | 5
13 |  | A0012 シーズン修正 (popup) |  | 2 | 0.6 | 1.4 | 2 | 0.6 | 1.4 | 0
14 | 目標 | A0006 目標登録 |  | 3 | 0.9 | 2.1 | 3 | 0.9 | 2.1 | 0
15 | 身体状況 | A0008 身体状況登録 |  | 3 | 0.9 | 2.1 | 3 | 0.9 | 2.1 | 5
15 |  | 体重計からBluetooth取り込む |  | 5 | 1.5 | 3.5 | 5 | 1.5 | 3.5 | 5
16 | メッセージ | A0013 グループメッセージ |  | 5 | 1.5 | 3.5 | 5 | 1.5 | 3.5 | 5
17 |  | A0016 グループメッセージ詳細 |  | 4 | 1.2 | 2.8 | 4 | 1.2 | 2.8 | 0
18 | Myページ | A0004 Myページ |  | 5 | 1.5 | 3.5 | 5 | 1.5 | 3.5 | 0
19 |  | 退会 Deactive |  | 1 | 0.3 | 0.7 | 1 | 0.3 | 0.7 | 0
20 |  | A0005 基本情報登録 |  | 4 | 1.2 | 2.8 | 4 | 1.2 | 2.8 | 0
21 |  | Create Material themes for App |  | 4 | 1.2 | 2.8 | 4 | 1.2 | 2.8 | 6
22 |  | Base Application + Setup API |  | 4 | 1.2 | 2.8 | 4 | 1.2 | 2.8 | 6

## 03_Infrastructure
|  |  | ESTIMATION |  |  | No: BM-2-901-22
Version: 1.5
Issue Date: 10/03/2026
SUN ASTERISK VIETNAM CO., LTD | [5 empty] | ISO/IEC 27001:2022 & ISO 9001:2015
Infrastructure
Total (MM) |  |  |  | 0.78 | 0.234
No | Category | Feature | Task | Effort（Man-days） |  | Note
Infrastructure
|  |  |  | Implement | FixBug
1 | アカウント | A0001 ログイン |  | 2 | 0.6
2 |  | A0005 アカウント新規登録 |  | 1 | 0.3
3 |  | A0002 PW再発行 |  | 3 | 0.9
4 |  | A0003 PW再設定 |  | 4 | 1.2
5 | 情報推移 | A0011 各種情報推移 |  | 2 | 0.6

## 04_Infrastructure for AWS
|  | ESTIMATION FOR AWS | [5 empty] | No: BM-2-901-22
Version: 1.5
Issue Date: 10/03/2026
SUN ASTERISK VIETNAM CO., LTD | [7 empty] | ISO/IEC 27001:2022 & ISO 9001:2015
* Dữ liệu trong bảng chỉ mang tính chất tham khảo. |  |  |  | DEVELOPMENT |  | STAGING |  | PRODUCTION
| Total (MM) |  |  | 2.7 | 0.8 | 0.9 | 0.6 | 0.9 | 0.6 | Note
No | Category | Feature |  | Effort（Man-hours） |  | Effort（Man-hours） |  | Effort（Man-hours）
|  |  |  | Implement | Test/Fix | Implement | Test/Fix | Implement | Test/Fix
1 | Designing Infra | Infrastructure architecture |  | 2 | 1 | 0 | 0 | 0 | 0 | Design + est cost infra
|  | Estimate infrastructure cost and performance system |  | 2 | 1 | 0 | 0 | 0 | 0
2 | Config AWS account | Create & Config AWS Account with AWS Organization |  | 2 | 1 | 0 | 0 | 0 | 0 | Centrally manage and govern your environment
3 | Domain | Create domain on AWS or Create hosted zones and add NS record to Japan site for management |  | 2 | 1 | 0 | 0 | 0 | 0 | Manage dns
4 | Building AWS Environment | Network | - VPC | 6 | 1.8 | 1.8 | 1.44 | 1.8 | 1.44 | Network for AWS
- Config Subnets (Private & Public)
- ACL for Private & Public
- VPC Endpoint
- Setting EIPs
- NAT gateway, Internet Gateway & Add Routing
|  | Route 53 | - Create ACM/SSL | 2 | 0.6 | 0.6 | 0.48 | 0.6 | 0.48 | Manage customer's domain
- Create records/sub domain
|  | IAM User | - IAM-User | 4 | 1.2 | 1.2 | 0.96 | 1.2 | 0.96 | Grant permission for user to access AWS console
- IAM-Group (Readonly, Admin, Power, Development)
- IAM-Policy for User & Group
|  | RDS Aurora | - Create Security Group, Subnet group, Parameter group | 3 | 0.9 | 0.9 | 0.72 | 0.9 | 0.72 | Database SQL
- Create RDS Cluster
- Create RDS Cluster Instance
- Setting schedule backup database
|  | RDS | - Create Security Group, Subnet group, Parameter group | 3 | 0.9 | 0.9 | 0.72 | 0.9 | 0.72 | Database SQL
- Create RDS Instance
- Setting schedule backup database
|  | Dynamodb | - Create table | 3 | 0.9 | 0.9 | 0.72 | 0.9 | 0.72 | Database NoSQL
- Create IAM role
|  | Elasticache | - Create Security Group, Subnet group, Parameter group | 3 | 0.9 | 0.9 | 0.72 | 0.9 | 0.72 | Redis
- Create Cluster
- Setting schedule backup redis
|  | Cognito | - Create user pool | 4 | 1.2 | 1.2 | 0.96 | 1.2 | 0.96 | Authentication - SSO
- Sign in through external federated identity providers
|  | S3 for application | - Create bucket and setting S3 policy | 1 | 0.3 | 0.3 | 0.24 | 0.3 | 0.24 | Store static files of Application
- S3 setting event
|  | S3 for log storage | - Create bucket and setting S3 policy | 1 | 0.3 | 0.3 | 0.24 | 0.3 | 0.24 | Store logs of ALB, CloudFront, and CloudTrail
- S3 setting event
|  | SNS | - Create topic | 2 | 0.6 | 0.6 | 0.48 | 0.6 | 0.48 | Push notification
- Setting policy, subscribe for alarm
|  | SSL | - Request certificate in ACM | 2 | 0.6 | 0.6 | 0.48 | 0.6 | 0.48 | Certificate for domain
|  | Cloudfront for ALB | - Create distribution, create origin | 4 | 1.2 | 1.2 | 0.96 | 1.2 | 0.96 | Setting content delivery network (CDN)
- Create cache policy
- Setting behavior
|  | Cloudfront for Frontend | - Create distribution, create origin | 4 | 1.2 | 1.2 | 0.96 | 1.2 | 0.96 | Setting content delivery network (CDN)
- Create cache policy
- Setting behavior
- Create bucket and setting S3 policy
|  | Lambda for Application | - Create function | 4 | 1.2 | 1.2 | 0.96 | 1.2 | 0.96 | Handles certain business logic of the system
- Create IAM role
- Deploy function
|  | Lightsail Mysql | - Create Database Mysql | 4 | 1.2 | 1.2 | 0.96 | 1.2 | 0.96 | AWS Lightsail MySQL is a managed database service that simplifies setting up, managing, and scaling MySQL databases in the cloud
- Setting Database
- Schedule backup database
|  | Lightsail Instance | - Create Instance | 4 | 1.2 | 1.2 | 0.96 | 1.2 | 0.96 | AWS Lightsail Instance is a virtual server that provides simplified cloud hosting with predictable pricing.
- Install and setting
- Backup Insntace
|  | Lightsail Bucket | - Create bucket | 2 | 0.6 | 0.6 | 0.48 | 0.6 | 0.48 | AWS Lightsail Bucket provides scalable object storage for storing and managing data like images, videos, and backups.
|  | Lightsail Load Balancer | - Create Load Balancer | 2 | 0.6 | 0.6 | 0.48 | 0.6 | 0.48 | AWS Lightsail Load Balancer distributes traffic across instances for high availability and automatic scaling.
- Setting route, ssl
|  | SES | - Verify domain - verify email | 2 | 0.6 | 0.6 | 0.48 | 0.6 | 0.48 | Send email
- Move out sandbox (if need)
|  | SQS | - Create queue | 2 | 0.6 | 0.6 | 0.48 | 0.6 | 0.48 | Message Queue
- Config queue
|  | Amplify | - Create new app | 8 | 2.4 | 2.4 | 1.92 | 2.4 | 1.92 | Host your simple marketing website or web application on AWS
- Connect to repository
- Confirm build configure
- Deploy code to amplify
|  | Backup | - Create Backup plan, Backup vault | 4 | 1.2 | 1.2 | 0.96 | 1.2 | 0.96 | AWS Backup automates and manages the backup of data across AWS services, ensuring data protection and compliance
- Associate with resources
|  | OpenSearch | - Create domain | 3 | 0.9 | 0.9 | 0.72 | 0.9 | 0.72 | Setup Search Engine
- Config domain
|  | API Gateway | - Create API Gateway | 4 | 1.2 | 1.2 | 0.96 | 1.2 | 0.96 | API Gateway acts as a front door for applications, enabling secure and controlled access to backend services by managing and routing API requests
- Create resource
- Create method
- Create stage
|  | GuardDuty | - Enable | 4 | 1.2 | 1.2 | 0.96 | 1.2 | 0.96 | Amazon GuardDuty is a threat detection service that continuously monitors your AWS accounts and workloads for malicious activity and unauthorized behavior
- Setting data sources
- Setting findings and notifications
|  | Config | - Enable | 3 | 0.9 | 0.9 | 0.72 | 0.9 | 0.72 | AWS Config enables you to assess, audit, and evaluate the configurations of your AWS resources to ensure compliance and secure management
- Setting rules and notifications
|  | BedRock | - Enable access model | 4 | 1.2 | 1.2 | 0.96 | 1.2 | 0.96 | AWS Bedrock is a fully managed service that helps build and scale generative AI applications using pre-built models from leading AI providers
- Setup permission
|  | WAF | - Create Web ACL | 3 | 0.9 | 0.9 | 0.72 | 0.9 | 0.72 | Web application firewall for CloudFront, ALB
- Config rule
|  | QuickSight | - Create QuickSight | 8 | 2.4 | 2.4 | 1.92 | 2.4 | 1.92 | Amazon QuickSight is a fast, cloud-powered business intelligence service that makes it easy to create and publish interactive dashboards
- Config and connect Data Source
- Add user and permission
|  | Bastion Host | - Create Security group | 4 | 1.2 | 1.2 | 0.96 | 1.2 | 0.96 | Configured to withstand any network attacks
- Create IAM role
- Create Instance EC2
- Setting server
|  | Container Registry (ECR) | - Create and setting life cycle | 1 | 0.3 | 0.3 | 0.24 | 0.3 | 0.24 | Create a repository (store images)
|  | Cluster ECS | - Create cluster | 1 | 0.3 | 0.3 | 0.24 | 0.3 | 0.24 | Cluster ECS
|  | Build & Deploy ECS Service Backend 1 | - Setting ALB, Target Group for ALB (HTTP & HTTPS) | 16 | 4.8 | 4.8 | 3.84 | 4.8 | 3.84
- Security Group for ALB
- Create IAM role
- Push image and deploy services
- Create/Setting AutoScale
|  | Build & Deploy ECS Service Backend 2 | - Setting ALB, Target Group for ALB (HTTP & HTTPS) | 10 | 3 | 3 | 2.4 | 3 | 2.4
- Security Group for ALB
- Create IAM role
- Push image and deploy services
- Create/Setting AutoScale
|  | Build & Deploy ECS Service Worker | - Security Group for Service | 8 | 2.4 | 2.4 | 1.92 | 2.4 | 1.92
- Create IAM role
- Push image and deploy services
- Create/Setting AutoScale
|  | Build & Deploy ECS Service Batch | - Security Group for Service | 8 | 2.4 | 2.4 | 1.92 | 2.4 | 1.92
- Create IAM role
- Push image and deploy services
- Setup ECS schedule
|  | AWS Batch | - Create computer environment | 8 | 2.4 | 2.4 | 1.92 | 2.4 | 1.92
- Create job queue
- Setting schedule job
|  | CI/CD for ECS Service Backend 1 | - Setup Github Action | 16 | 4.8 | 4.8 | 3.84 | 4.8 | 3.84
- Setup Code Pipeline
- Setup S3 store artifact
- Setup Code Build
- Setup Code Deploy
|  | CI/CD for ECS Service Worker | - Setup Github Action | 10 | 3 | 3 | 2.4 | 3 | 2.4
- Setup Code Pipeline
- Setup S3 store artifact
- Setup Code Build
|  | CI/CD for Cloudfront & S3 | - Setup Github Action | 16 | 4.8 | 4.8 | 3.84 | 4.8 | 3.84
- Setup S3 store artifact
- Setup Code Pipeline
- Setup Code Build
- Setup Lambda
|  | CI/CD for EC2 in AutoScale | - Setup Github Action | 16 | 4.8 | 4.8 | 3.84 | 4.8 | 3.84
- Setup Code Pipeline
- Setup S3 store artifact
- Setup Code Build
- Setup Code Deploy
|  | CI/CD for Serverless Lambda | - Setup Github Action | 16 | 4.8 | 4.8 | 3.84 | 4.8 | 3.84
- Setup S3 store artifact
- Setup Code Pipeline
- Setup Code Build
|  | CloudTrail | - Create cloudtrail | 1 | 0.3 | 0.3 | 0.24 | 0.3 | 0.24 | Create cloudtrail store all event history of your AWS account
5 | Setting CloudWatch Alarm | ECS Database RDS Elasticache Redis ALB WAF ... etc | 1. Set CloudWatch Alarm with CPU, Memory, Storage, Latency Read/Write, ... | 24 | 7.2 | 7.2 | 5.76 | 7.2 | 5.76 | Send alarm to Slack
SNS Permision & IAM Role for Lambda
SNS & Lambda to Push Notify
Coding for Lambda function (Python) send message to Chatwork/Slack
|  | Billing/Cost - AWS Budget | SNS Permision & IAM Role for Lambda | 2 | 0.6 | 0.6 | 0.48 | 0.6 | 0.48
SNS & Lambda to Push Notify
Coding for Lambda function (Python) send message to Chatwork/Slack
6 | Document | All information about infrastructure, system, configuration, deployment, monitoring |  | 21 | 0 | 14 | 0 | 14 | 0 | Document

## 05_Resource plan
|  |  | ESTIMATION | [14 empty] | No: BM-2-901-22
Version: 1.5
Issue Date: 10/03/2026
SUN ASTERISK VIETNAM CO., LTD | [17 empty] | ISO/IEC 27001:2013&ISO 9001:2015
* Unit: Man-month
| Role | Requirement Definition |  |  | Basic Design |  |  | Detail Design/Coding/Unit Test | [7 empty] | Intergration Testing/System Test |  |  |  | UAT |  | Total
|  | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01
| 【SJP】Designer | [20 empty] | 0
| 【SVN】PL | [20 empty] | 0
| 【SVN】BrSE | [20 empty] | 0
| 【SVN】Backend Lead | [20 empty] | 0
| 【SVN】Backend | [20 empty] | 0
| 【SVN】Frontend Lead | [20 empty] | 0
| 【SVN】Frontend | [20 empty] | 0
| 【SVN】Native-app Lead | [20 empty] | 0
| 【SVN】Native-app | [20 empty] | 0
| 【SVN】QA Lead | [20 empty] | 0
| 【SVN】QA | [20 empty] | 0
| 【SVN】Infrastructure | [20 empty] | 0
| 【SJP】Designer | [20 empty] | 0
| 【SVN】Designer | [20 empty] | 0
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total phase | 2026-01-01: 0; 2026-04-01: 0; 2026-07-01: 0; 2027-03-01: 0; 2027-07-01: 0

## Appendix
|  | ESTIMATION | No: BM-2-901-22
Version: 1.5
Issue Date: 10/03/2026
SUN ASTERISK VIETNAM CO., LTD |  |  | ISO/IEC 27001:2022 & ISO 9001:2015
Value | Coefficient | Note
Buffer | 0.3 | 30%
Unit Test | 0.7 | Coefficient*Implement effort
Unit Test (for AWS) | 0.5 | Coefficient*Implement effort
Fixbug | 0.3 | Coefficient*Implement effort
Management | 0.2 | Coefficient*Implement effort
Working days in a month | 20
Working hours in a day | 7
* Have to estimate base on qualification of rank 3.5 developer
* FrontEnd implement effort includes effort to integrate with backend and markup...etc...
Development Strategy | Type of service | Web Rendering Method | Admin template | Server/Serverless | IaC tool
MVP / POC | Web | Server Side Redering (SSR) | AdminLTE | Server | Terraform
Full feature / MMP | Mobile app | Client Side Rendering (CSR) | FilamentPHP | Serverless | CloudFormation
| PWA (Progressive Web App) | Pre-Rendering: Server Side Rendering (Universal SSR) | LaravelAdmin |  | Bicep
|  | Pre-Rendering: Static Site Generation (SSG) |  |  | Ansible
|  | Dynamic Rendering |  |  | Chef
Puppet
CDK

## Project Organization Structure
| ESTIMATION | No: BM-2-901-22
Version: 1.5
Issue Date: 10/03/2026
SUN ASTERISK VIETNAM CO., LTD |  | ISO/IEC 27001:2022 & ISO 9001:2015
Vu Xuan Dung
(Director)
Tran Van Tan
(Project Management)
BrSE
XXX PROJECT STRUCTURE（１１月～０５月）
Customer team
Window １
Window ２
SJP Team
Consultant
Director
Development team
iOS team
iOS Developer １
iOS Developer ２
Other
Designer １
Infra １
Android team
Android Developer １
AndroidDeveloper ２
Ruby team
Ruby Developer １
Ruby Developer ２
QA team
QA１
QA２