## History of changes
|  | MILESTONES TEMPLATE | No: BM-2-901-42
Version: 1.1
Issue Date: 05/04/2021
SUN ASTERISK VIETNAM CO., LTD |  |  | ISO/IEC 27001:2013&ISO 9001:2015
LỊCH SỬ THAY ĐỔI
No | Change Item | Description of changes | Change Date
1 |  | Ban hành mới | 2020-08-09
2 |  | Update format | 2021-05-04

## (EN) Milestones
[12 empty] | MILESTONES TEMPLATE | [33 empty] | No: BM-2-901-42
Version: 1.1
Issue Date: 05/04/2021
SUN ASTERISK VIETNAM CO., LTD | [45 empty] | ISO/IEC 27001:2013&ISO 9001:2015
| Scope ◆ {{Company name}}: · Provide specifications and design · Answer questions from Sun * · Verification ◆ Sun *: · Implementation · Report implementation progress · Verification · Bugs · Response to issues | [17 empty] | Release version definition ◆ Alpha version: December 12 (prediction) · Implementation completed · Ready to start Sun * verification ◆ β version: January 3 (prediction) · Sun * verification completed · If there is a bug, fix it during the buffer period (β version to RC version). · {{Company name}} can perform integrated verification. ◆ RC version: February 21 (planned) · Version with no bugs | [18 empty] | *important point ◆ Milestones created based on the following sheet calculations https://link.sun-asterisk.vn/Jyssd0 ◆ The quote in the upper right navigation is not yet included
Milestones
| 8 | [30 empty] | 9 | [29 empty] | 10 | [30 empty] | 11 | [29 empty] | 12 | [30 empty] | 1 | [30 empty] | 2
 | time axis 2019-08-01 to 2020-03-05
| K I C K O F F | [8 empty] | Company holidays | [22 empty] | Independence Day | [100 empty] | α Version | [19 empty] | New Year |  | β Version | [19 empty] | Lunar New Year holidays | [28 empty] | R C Version

## (JA) Milestones
[12 empty] | MILESTONES TEMPLATE | [33 empty] | No: BM-2-901-42
Version: 1.1
Issue Date: 05/04/2021
SUN ASTERISK VIETNAM CO., LTD | [45 empty] | ISO/IEC 27001:2013&ISO 9001:2015
| 対応範囲/Scope ◆ {{会社名}}: · 仕様書・デザイン提供 · Sun*からの質問を回答 · 検証 ◆ Sun*: · 実装 · 実装進捗を報告 · 検証 · バグ修正 · 指摘対応 | [17 empty] | リリース版定義/Release version definition ◆ α版：12月12日（予想） · 実装完了 · Sun*検証着手できる状態 ◆ β版：1月3日（予想） · Sun*検証完了 · バグがあれば、バッファー期間（β版〜RC版）で修正します。 · {{会社名}}側が統合検証できる。 ◆ RC版：2月21日 (予定） · バグがなくなった版 | [18 empty] | ＊注意点 ◆以下のシートの計算をベースして作成されたマイルストーン https://link.sun-asterisk.vn/Jyssd0 ◆ 右上ナビゲーションの見積がまだ含まない
Milestones
| 8月 | [30 empty] | 9月 | [29 empty] | 10月 | [30 empty] | 11月 | [29 empty] | 12月 | [30 empty] | 1月 | [30 empty] | 2月
 | time axis 2019-08-01 to 2020-03-05
K I C K O F F
WF作成
[14 empty] | デザイン作成 | [18 empty] | 独
[21 empty] | デザインレビュー | [11 empty] | 立
[10 empty] | 社内旅行 | [22 empty] | 記 |  | 開発 | [11 empty] | 開発 | [106 empty] | 新 | [21 empty] | 旧正月連休
[33 empty] | 念 | [20 empty] | 結合テスト | [99 empty] | 年
[33 empty] | 日 | [34 empty] | 受入テスト
α版リリース
メンテナンス
β版リリース

## General
|  | MILESTONES TEMPLATE | No: BM-2-901-42
Version: 1.1
Issue Date: 05/04/2021
SUN ASTERISK VIETNAM CO., LTD |  |  | ISO/IEC 27001:2013&ISO 9001:2015
Holiday
# | Date | Description
1 | 2019-08-10 | 社内旅行
2 | 2019-08-11 | 社内旅行
3 | 2019-08-12 | 社内旅行
4 | 2019-08-13 | 社内旅行
5 | 2019-08-14 | 社内旅行
6 | 2019-09-02 | 独立記念日
7
8
9
10
11