Risk Management Guidelines

I. Introduction	1

1.1 Purpose - Mục đích	1

1.2 Definitions - Các thuật ngữ	1

1.3 Key relevant documents - Các tài liệu liên quan	2

II. Guidelines - Nội dung hướng dẫn	2

2.1 Risk Assessment	2

2.1.1 Identify Risk	2

2.1.2 Analyze Risk	2

2.2 Risk Control	4

2.3 Review Risk	5

# I. Introduction

## 1.1 Purpose - Mục đích

Purpose of this document is to guide risk management activities in projects

## 1.2 Definitions - Các thuật ngữ

| No | Terminology |  | Explanation |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Risks |  | are those events or conditions that may occur, and if it does take place, has a harmful or negative effect on a project |  |  |  |  |  |  |  |
| 2 | Risk Sources |  | are the fundamental drivers that cause risks within a project or organization. There are many sources of risks, both internal and external to a project. Risk sources identify common areas where risks may originate |  |  |  |  |  |  |  |
| 3 | Risk Description |  | are the description about risk within a project or organization. |  |  |  |  |  |  |  |
| 3 | Risk Categories |  | reflect the “bins” for collecting and organizing risks. A reason for identifying risk categories is to help in the future consolidation of the activities in the risk mitigation plans |  |  |  |  |  |  |  |
| 4 | Probability |  | How likely is this risk to occur? |  |  |  |  |  |  |  |
| 5 | Impact |  | How bad will it be if this risk happens? |  |  |  |  |  |  |  |
| 6 | Priority |  | What prior to this risk to manage and resolve? |  |  |  |  |  |  |  |
| 6 | Priority |  | is a simple calculation that gives a value to setting risk priority |  |  |  |  |  |  |  |
| 8 | Trigger |  | determines how to know if the risk occurs so you’ll know when and if put contingency action in place. |  |  |  |  |  |  |  |
| 9 | Mitigation Plan |  | are the plans taken BEFORE those risks occur to reduce the probability and/or the impact of risks. |  |  |  |  |  |  |  |
| 10 | Contingency Plan |  | are the plans taken AS those risks do occur to reduce their impact. |  |  |  |  |  |  |  |

## 1.3 Key relevant documents - Các tài liệu liên quan

| No. | Document Name | Link |
| --- | --- | --- |
| 1 | Risk Management Template | https://goo.gl/fMTFuB |

# II. Guidelines - Nội dung hướng dẫn

## 2.1 Risk Assessment

### 2.1.1 Identify Risk

① Study list of commonly occurring risks from similar project and advisor to get information about risk and risk management.

② Evaluating and thinking about previously encountered risks also help to identify other risks that may be pertinent to this project but do not appear on the list.

③ Go through one-by-one Risk Source & Risk Category and use judgment & experience to evaluate the situation to identify potential risks. Another alternative is to use the project kick-off meetings to elicit views on risks from others.
④ The identified risk will be log into Risk Management Sheet

### 2.1.2 Analyze Risk

Estimate the probability of risk occurrence and impact when the risk does occur, then determine the priority of the risk.

*Estimate Probability of risk: Estimate the likelihood that the risk will occur:

| Probability | Explanation |
| --- | --- |
| Low (1) | Has happened very infrequently or is expected not to happen |
| Medium (2) | Has happened occasionally or has a reasonable but not completely expected chance of happening in the future |
| High (3) | Exhibits the high risk cue, has happened frequently, has a very significant chance of happening in the future |

*Estimate Impact of risk: Estimate the impact as Low, Medium or High as the table below:

| Impact | Explanation |
| --- | --- |
| Low (1) | < 5% project size affected Or Minor areas of project scope affected < 5% project effort /cost increase < 5% project duration increase |
| Medium (2) | 5% - 10% project size affected 5% - 10% project effort /cost increase 5% - 10% project duration increase |
| High (3) | > 10% project size affected Or Minor areas of project scope affected > 10% project effort /cost increase > 10% project duration increase |

*Prioritize risk: After determining the probability and estimating the impact of the risk, risks are prioritized according to their potential implications for having an effect on the project's objectives. As depicted in probability and impact matrix table below, the combinations of probability and impact that lead a risk being rated as "Trivial, Minor, Major, Critical, Blocker)

The risks will be prioritized as Blocker > Critical > Major > Minor > Trivial.

| Impact | Low (1) | Medium (2) | High (3) |
| --- | --- | --- | --- |
| Probability |  |  |  |
| Low (1) | 1 (Trivial) | 2 (Minor) | 3 (Major) |
| Medium (2) | 2 (Minor) | 4 (Major) | 6 (Critical) |
| High (3) | 3 (Major) | 6 (Critical) | 9 (Blocker) |

## 2.2 Risk Control

Develop Risk Response Plan: Once the risks have been prioritized, determine the response to each identified risk by examining and choosing the best approach. Possible Responses to risk are:

| Risk Response | Action |  |  |  |  | Criteria |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Manage | There are certain risks that cannot be eliminated. However, their impact can be reduced. Mitigation & Contingency actions are required, taking early action to reduce the probability and/or impact of a risk is often more effective than trying to repair the damage after the risk has occurred. |  |  |  |  | Risk Priority is Major/ Critical/ Blocker |  |
| Avoid | Focus on eliminating the cause and thus, eliminating the threat. |  |  |  |  |  |  |
| Transfer | Transfer the risk to some other party. Insurance purchases, warranties, guarantees, etc are examples of risk transfers |  |  |  |  |  |  |
| Accept | No plan to deal with the risk The project can live with the consequences if the risk actually occurs. |  |  |  |  | Risk Priority is Trivial/ Minor OR Unable to identify another suitable strategy |  |

*Plan Mitigation actions needed to reduce the probability and/or the impact of risks before those risks occur. The mitigation plan is required for Major/ Critical/ Blocker Risks.

*Plan Contingency actions to reduce the impact if a risk does occur. Again, it is just mandatory to develop contingencies for High and Medium Risk.

* Manage risks: 
- Response to risk using risk response plan when the risk occurs.
- Communicate risk status to relevant stakeholders.
- Report project risk status as component of sprint or milestone report.
※ Risk list will be submitted to the organizational process asset for subsequent projects usage.

## 2.3 Review Risk

- Monitor the risks frequently on sprint basic or event-driven:

+ Define the review day of the defined risks.

+ Check the result of risk and the efficiency of mitigation/ Contingency Plan

+ Close any risk that poses no threat to the project

+ Track risk progress
- At the end of projects, update Project Risk List as part of Close Project Meeting Report.