## History of changes
|  | COMMUNICATION PLAN | No: BM-QT-1701-26
Version: 1.4
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD |  |  | ISO/IEC 27001:2013&ISO 9001:2015
HISTORY OF CHANGES
No | Change Item | Description of changes | Change Date
1 |  | Add new | 15/05/2020
2 |  | Update format | 2021-05-04
3 | All sheet | Thay đổi Project Role theo thay đổi cơ cấu mới của tổ chức - Remove role SM, GL, PL - Add mới role PSM | 2021-11-08
4 | All sheet | Thay đổi Project Role theo thay đổi cơ cấu mới của tổ chức - Unit Manager thay đổi thành Software Delivery Manager - PSM thay đổi thành Project Leader | 2024-12-23
5 | All sheet | Update mã biểu mẫu theo tiêu chuẩn ISO. | 22/09/2026

## Communication Plan
|  | COMMUNICATION PLAN | [6 empty] | No: BM-2-901-38
Version: 1.3
Issue Date: 23/12/2024
SUN ASTERISK VIETNAM CO., LTD | [8 empty] | ISO/IEC 27001:2013&ISO 9001:2015
STT | Communication |  | PIC | Attendance | Content | Frequency | Timebox | Method | Report Format/ Attached File | Note
1 | Personal Daily Report |  | Team Member |  | Report personnal daily progress made on project tasks | Everyday |  | ChatTool
2 | Daily meeting |  | Project Lead/BrSE | Team Members | Each team members briefly describes any “completed” contributions and any obstacles that stand in their way. | Everyday | 15 - 20 mins | Face to Face | The daily meeting is structured around some variant of the following three questions: 1. What have you completed since the last meeting? 2. What do you plan to complete by the next meeting? 3. What is getting in your way? | 8:00 am to 8:15 am every day
3 | Sprint Planning Meeting |  | Project Lead/BrSE | Project Lead/BrSE Team Member | The team determines the product backlog items they will work on during that sprint and discuss their initial plan for completing those product backlog items. | Every Sprint |  | MTG Room |  | 1 tuần 1 lần hoặc 1 sprint 1 lần 8:00 am to 9:00 am thứ 6 hàng tuần
4 | Sprint Review Meeting (Internal/External) |  | Project Lead/BrSE | Customers Project Lead/BrSE Team Member | The purpose of the Sprint Review meeting is for the team to show the customers and stakeholders the work they have accomplished over the sprint and compare it to the commitment given at the beginning of the sprint. | Every Sprint |  | Video Call |  | 1 tuần 1 lần hoặc 1 sprint 1 lần 8:00 am to 9:00 am thứ 6 hàng tuần
5 | Retrospective meeting |  | Project Lead/BrSE | Project Lead Team Members | retrospective meetings are intended to reflect on the most recent sprint/project/milestone and identify areas that need improvement and celebrate team wins. | Every Sprint |  | MTG Room |  | 3:00 pm ngày thứ 6 cuối cùng mỗi tháng
Others

## SelectList
Frequency
No | Category | NOTE
1 | Everyday
2 | Every week
3 | Every two week
4 | Every Phase
5 | Every Sprint
6 | One time
7 | When needed
Tool
No | Category | NOTE
1 | Face to Face
2 | Video Call
3 | ChatTool | Chatwork, Slack....
4 | Email
5 | MTG Room