## History of changes
|  | PROJECT KPI DATA | No: BM-QT-1706-01
Version: 1.6
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD |  |  | ISO/IEC 27001:2013&ISO 9001:2015
LỊCH SỬ THAY ĐỔI
STT | Mục thay đổi | Nội dung | Ngày thay đổi
1 |  | Ban hành mới | 15/05/2020
2 |  | Sửa đổi: 2. Project information : thêm 2 trường Start date, End date 3. Weekly raw data: thêm 2 cột Start Phase, End Phase Thêm mới: 6. KPI analysis | 31/8/2020
3 |  | Sửa đổi: 1. Overview : Thay thế 7 chỉ số thành 6 chỉ số, điều chỉnh tiêu chuẩn của mỗi chỉ số 2. Weekly raw data: thêm mới tiêu chí :Spent time for fixing bug in a period of report (Hours) Quy đổi đơn vị tính effort từ manday thành man hour | 2021-07-18
4 |  | Update format | 2021-05-04
5 | Sheet Project Information | Thay đổi Project Role theo thay đổi cơ cấu mới của tổ chức - Remove role SM, GL, PL - Add mới role PSM | 2021-11-08
6 | Overview Sheet | Thay đổi công thức Estimation Accuracy - Modify (Total Actual Effort / Total Estimated Effort) * 100 | 2022-01-19
7 | Sheet Project Information Sheet Weekly raw data | Sửa đổi: 2. Project information: thêm mới KPI Management Period. 3. Weekly raw data: thêm mới cột Phase dành cho những dự án quản lý KPI theo Phase. Thêm mới sheet: 4.2 Project Summary_By Phase: 5.2 Chart_By Phase | 2024-11-18
8 |  | Cập nhật Project role theo cơ cấu tổ chức mới của công ty: - PSM -> Project Leader (PL) - UM -> Software Delivery Manager (SDM) | 19/12/2024
9 | All sheet | Update mã biểu mẫu theo tiêu chuẩn ISO. | 22/09/2026

## 1. Overview
|  | PROJECT KPI DATA |  |  | No: BM-QT-1706-01
Version: 1.6
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD |  |  |  |  | ISO/IEC 27001:2013&ISO 9001:2015
I | PURPOSE
- | Record KPI data of project.
II | SCOPE
Apply to all of projects
III | REFERENCE MATERIAL
■ | Sun* KPI System_Introduction
IV | CONTENT
No. | Metrics | Calculation | Unit | Description | Note
1 | QA Bug Proportion (Q1) | Internal Bug Count / Total Actual Effort [MH] | Bug/Mh | The bug implementation proportion before a delivery process comparing with the team's actual effort. Internal Bug Count: Bug count found by QAs in our test processes: Integration-test and System-test. Total Actual effort: Unit: Man-Hours Total spent time on some activities as below. UI Design System Design Implementation QA Testing Bug FixingRetestingetesthe t If teamRedminedmine (both old redmineRedminedmine Pherusa), the total actual effort is the sum of all spent time in the period of the report.
2 | UAT Bug Rate (Q2) | ( UAT Bug Count/ All Bug Count ) * 100 | % | The rate of bug in UAT comparing with all bugs found in some test processes: QA test and UAT test. UAT Bug Count: The bug count found in UAT phase. Usually this bugs are reported by our client. All Bug Count: Total bug count which involves QA bug and UAT bug.
3 | Estimation Accuracy Rate (C1) | ( Total Actual Effort / Total Estimated Effort ) * 100 | % | Show the deviation of the actual actual effort compared to the estimated effort. Based on which to evaluate the efficiency of resource use in the project. - The unit of effort is hour.
4 | Bug Handling Cost Rate (C2) | ( Total Bug Handling Effort / Total Actual Effort ) * 100 | % | Show how much effort was spent for bug fixing and re-testing. Total Bug Handling Effort: Unit: Hour Bug fixing effort [h] + QA Re-testing effort [h] Total Actual Effort: Unit: Hour Total spent time recorded as actual activity effort. Need to adjust activity expression to meet with other metrics' one.
5 | Issue Closed Ratio (M1) | (Closed Issue Count / All Issue Count)*100 | %
■ | Sheet [Project Information] Ghi nhận những thông tin chung của dự án vào Sheet Project Information. *Lưu ý: Nếu dự án Release theo từng Phase, PL cần cung cấp thông tin KPI Management Period: By Phase để các sheet (4.2 Project Summary_By Phase, 5.2 Chart_By Phase) lên dữ liệu đúng với đặc thù dự án.
■ | Sheet [Weekly raw data sheet] - Hàng tuần, PL/BrSe/Teamleader dự án cập nhật raw data của dự án vào sheet này.
■ | Sheet [Project Summary] - Từ dữ liệu được chủ động cập nhật trong [Weekly raw data] Sheet , các chỉ số sẽ được tự động ghi nhận vào [Project Summary] Sheet này theo công thức đã được định sẵn. - Đối với dự án quản lý Release theo Sprint. các chỉ số KPI sẽ tự động ghi nhận vào 4.1 Project Summary_Sprint. - Đối với dự án quản lý Release theo Phase, các chỉ số KPI sẽ tự động ghi nhận đồng thời tại 4.1 Project Summary_Sprint. và 4.2 Project Summary_By Phase.
■ | Sheet [Chart] - Theo dõi xu hướng dự án theo các kỳ báo cáo để nhìn được những phản ánh từ data trong kỳ báo cáo đó. Gồm 5.1 Chart_By Sprint và 5.2 Chart_By Phase - Từ đó đưa ra giải pháp, hành động hoặc cần có sự tham gia các cấp lãnh đạo( trong trường hợp cần thiết)
Chỉ số Upper Control Limit(UCL) và Lower Control Limit(LCL), Target đã được Công ty tính toán, thống kê, chọn lựa thông qua dữ liệu của năm 2020 - Data của các tuần nếu nằm ngoài dải UCL/LCL sẽ cần phân tích và đưa ra action phù hợp( Nếu có)
No. | KPI metric | Unit | UCL | Target | LCL
1 | Q1 QA Bug Proportion | Bug/Md | 0.5 | 0.05 | 0
2 | Q2 UAT Bug Rate | % | 20 | 5 | 0
3 | C1 Estimation Accuracy Rate | % | 115 | 100 | 85
4 | C2 Bug Handling Cost Rate | % | 20 | 10 | 5
5 | M1 Issue Closed Ratio | % | 110 | 100 | 90

## 2. Project information
| PROJECT KPI DATA | No: BM-QT-1706-01
Version: 1.6
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD |  | ISO/IEC 27001:2013&ISO 9001:2015
Project name
CEV Center
PL
Team Leader
Customer
Status
Category | Development
KPI Management Period | By Phase
Team Size
Description
Start Date
End Date

## 3. Weekly raw data
|  | PROJECT KPI DATA | [9 empty] | No: BM-QT-1706-01
Version: 1.6
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD | [11 empty] | ISO/IEC 27001:2013&ISO 9001:2015
Phase | Sprint | Start date | End date | Q (Quality) Number of Internal QA bug in a period of report | Q (Quality) Number of Bug found in UAT phase in a period of report | C (Cost): Spent time in your project in a period of report (Hours) | C (Cost): Estimated time in your project in a period of report (Hours) | C (Cost) Spent time for fixing bug in a period of report (Hours) | M(Management) Number of ticket closed in a period of report | M(Management) Number of total ticket in a period of report | Other: If your project want to measure 1 or more other KPIs instead of company required ones, please record your idea here. Then PEC team will contact you to make clear your idea. | Which application do you report to? (Web, Mobile App, General) | Note
7
1 | 1 | 2024-03-07 | 2024-03-13 | 0 | 0 | 200 | 200 | 0 | 7 | 10 |  | Web
2 | 2 | 2024-03-14 | 2024-03-20 | 100 | 0 | 260 | 260 | 4 | 21 | 22
2 | 3 | 2024-03-21 | 2024-03-27 | 1 | 0 | 320 | 320 | 120 | 15 | 17
2 | 4 | 2024-03-28 | 2024-04-03 | 20 | 0 | 120 | 100 | 210 | 26 | 26
2 | 5 | 2024-04-04 | 2024-04-10 | 1 | 5 | 11 | 30 | 111 | 17 | 18
2 | 6 | 2024-04-11 | 2024-04-17 | 1 | 10 | 120 | 150 | 30 | 20 | 20
2 | 7 | 2024-04-18 | 2024-04-24 | 1 | 0 | 29 | 27 | 0 | 12 | 12
2 | 8 | 2024-04-25 | 2024-05-08 | 0 | 0 | 33.5 | 34.5 | 0 | 14 | 15
2 | 9 | 2024-05-08 | 2024-05-15 | 1 | 0 | 38.5 | 34 | 2 | 14 | 16
2 | 10 | 2024-05-15 | 2024-05-22 | 0 | 0 | 34.5 | 35.5 | 0 | 12 | 12
2 | 11 | 2024-05-22 | 2024-05-29 | 0 | 0 | 29.5 | 33 | 0 | 16 | 16
3 | 12 | 2024-05-29 | 2024-06-05 | 1 | 0 | 27 | 29 | 2 | 12 | 13
3 | 13 | 2024-06-05 | 2024-06-12 | 1 | 0 | 33.5 | 35 | 1 | 16 | 16
3 | 14 | 2024-06-12 | 2024-06-19 | 0 | 0 | 31.5 | 31.5 | 0 | 15 | 15
3 | 15 | 2024-06-19 | 2024-06-26 | 0 | 0 | 28.5 | 27 | 0 | 9 | 9
3 | 16 | 2024-06-26 | 2024-07-03 | 0 | 0 | 28 | 28.5 | 0 | 13 | 13
3 | 17 | 2024-07-03 | 2024-07-10 | 0 | 0 | 42.5 | 39 | 0 | 14 | 14
3 | 18 | 2024-07-10 | 2024-07-17 | 3 | 0 | 28 | 29 | 5 | 14 | 14
3 | 19 | 2024-07-17 | 2024-07-24 | 3 | 0 | 32.5 | 29.5 | 4 | 12 | 14
3 | 20 | 2024-07-24 | 2024-08-01 | 1 | 0 | 36 | 38.5 | 1 | 20 | 20
3 | 21 | 2024-08-01 | 2024-08-14 | 2 | 0 | 52 | 46.5 | 3.5 | 22 | 25
3 | 22 | 2024-08-14 | 2024-08-21 | 3 | 0 | 40 | 35 | 3.5 | 19 | 19
3 | 23 | 2024-08-21 | 2024-08-28 | 2 | 0 | 39 | 36.5 | 7 | 17 | 17
4 | 24 | 2024-08-28 | 2024-09-04 | 0 | 0 | 7 | 21 | 0 | 5 | 12
4 | 25 | 2024-09-04 | 2024-09-11 | 0 | 0 | 40.5 | 36 | 0 | 18 | 18
4 | 26 | 2024-09-11 | 2024-09-18 | 3 | 0 | 36 | 40 | 7 | 16 | 18
4 | 27 | 2024-09-18 | 2024-09-25 | 3 | 0 | 37 | 40 | 7 | 14 | 15
4 | 28 | 2024-09-25 | 2024-10-02 | 0 | 0 | 200 | 200 | 0 | 7 | 10
4 | 29 | 2024-10-02 | 2024-10-09 | 100 | 0 | 260 | 260 | 4 | 21 | 22
4 | 30 | 2024-10-09 | 2024-10-16 | 1 | 0 | 320 | 320 | 120 | 15 | 17
4 | 31 | 2024-10-16 | 2024-10-23
5 | 32 | 2024-10-23 | 2024-10-30
5 | 33 | 2024-10-30 | 2024-11-06
5 | 34 | 2024-11-06 | 2024-11-13
5 | 35 | 2024-11-13 | 2024-11-20
5 | 36 | 2024-11-20 | 2024-11-27
5 | 37 | 2024-11-27 | 2024-12-04
5 | 38 | 2024-12-04 | 2024-12-11
5 | 39 | 2024-12-11 | 2024-12-18
5 | 40 | 2024-12-18 | 2024-12-25

## 4.1 Project Summary_Sprint
|  | Project KPI Data | [5 empty] | No: BM-QT-1706-01
Version: 1.6
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD | [7 empty] | ISO/IEC 27001:2013&ISO 9001:2015
Sprint | Start phase | End phase | QA Bug Proportion (Q1) #/Mh Internal Bug Count / Total Actual Effort [MH] | UAT Bug Rate (Q2)% ( UAT Bug Count/ All Bug Count ) * 100 | Estimation Accuracy Rate (C1)% ( Total Actual Effort / Total Estimated Effort ) * 100 | Bug Handling Cost Rate (C2)% ( Total Bug Handling Effort / Total Actual Effort ) * 100 | Issue Closed Ratio (M1)% (Closed Issue Count / All Issue Count)*100 | Note
1 | 2024-03-07 | 2024-03-13 | 0 |  | 100 | 0 | 70 | Because one ticket was waiting for the client to review the PR, another ticket was waiting for stakeholders to respond, and three other tickets were awaiting review by a team member who was off that day.
2 | 2024-03-14 | 2024-03-20 | 0.38462 | 0 | 100 | 1.5385 | 95.4545
3 | 2024-03-21 | 2024-03-27 | 0.003125 | 0 | 100 | 37.5 | 88.2353 | In this sprint, one of our team members took 2 days off. When he returned to work, there were a lot of investigation reports and pull requests for him to review. These tasks took up his time and hindered him from handling the implementation tasks. Another reason is that the engineers spent time discussing the requirements of a new user story.
4 | 2024-03-28 | 2024-04-03 | 0.16667 | 0 | 120 | 175 | 100
5 | 2024-04-04 | 2024-04-10 | 0.090909 | 0.83333 | 36.6667 | 1009.0909 | 94.4444
6 | 2024-04-11 | 2024-04-17 | 0.0083333 | 0.90909 | 80 | 25 | 100
7 | 2024-04-18 | 2024-04-24 | 0.034483 | 0 | 107.4074 | 0 | 100
8 | 2024-04-25 | 2024-05-08 | 0 |  | 97.1014 | 0 | 93.3333
9 | 2024-05-08 | 2024-05-15 | 0.025974 | 0 | 113.2353 | 5.1948 | 87.5 | During this sprint, there were some investigation tickets related to new pages and features that the team had not encountered before. This is why the investigation took longer than expected.
10 | 2024-05-15 | 2024-05-22 | 0 |  | 97.1831 | 0 | 100
11 | 2024-05-22 | 2024-05-29 | 0 |  | 89.3939 | 0 | 100
12 | 2024-05-29 | 2024-06-05 | 0.037037 | 0 | 93.1034 | 7.4074 | 92.3077
13 | 2024-06-05 | 2024-06-12 | 0.029851 | 0 | 95.7143 | 2.9851 | 100
14 | 2024-06-12 | 2024-06-19 | 0 |  | 100 | 0 | 100
15 | 2024-06-19 | 2024-06-26 | 0 |  | 105.5556 | 0 | 100
16 | 2024-06-26 | 2024-07-03 | 0 |  | 98.2456 | 0 | 100
17 | 2024-07-03 | 2024-07-10 | 0 |  | 108.9744 | 0 | 100
18 | 2024-07-10 | 2024-07-17 | 0.10714 | 0 | 96.5517 | 17.8571 | 100
19 | 2024-07-17 | 2024-07-24 | 0.092308 | 0 | 110.1695 | 12.3077 | 85.7143 | C1: Engineer took time for self-testing in stg environment. M1: Clients visited and had a lot of mtgs and team events. The team and clients had decided in advance to consider this as a special sprint.
20 | 2024-07-24 | 2024-08-01 | 0.027778 | 0 | 93.5065 | 2.7778 | 100
21 | 2024-08-01 | 2024-08-14 | 0.038462 | 0 | 111.828 | 6.7308 | 88 | Took time supporting new members. There was a user story requirement that needed to wait for stakeholder confirmation. The discussion during the review phase took time.
22 | 2024-08-14 | 2024-08-21 | 0.075 | 0 | 114.2857 | 8.75 | 100 | The new engineer took more time than expected because it was his first task, so it was still hard to estimate correctly, and he also needed time to get used to the project.
23 | 2024-08-21 | 2024-08-28 | 0.051282 | 0 | 106.8493 | 17.9487 | 100
24 | 2024-08-28 | 2024-09-04 | 0 |  | 33.3333 | 0 | 41.6667 | - The reviewer from the client took 2 days off so the PR review process was delayed quite a lot. - An engineer in the team took an unexpected day off and after coming back there are some issues that he need to catch up and resolve with the team so the ticket situation of him was also delayed
25 | 2024-09-04 | 2024-09-11 | 0 |  | 112.5 | 0 | 100 | There is a ticket that costed more time than the engineer expected, it's the task for testing the script to check the inconsistency data between DB and Hubspot created and tested by the engineer but the engineer is not familiar with the system so it took more time for him to prepare the data and the document to report about the test result.
26 | 2024-09-11 | 2024-09-18 | 0.083333 | 0 | 90 | 19.4444 | 88.8889 | During this sprint, there are some tickets that costed the team more time to implement and fix comment so the team didn't have chance to handle some other tickets then the number of closed ticket does not meet the standard.
27 | 2024-09-18 | 2024-09-25 | 0.081081 | 0 | 92.5 | 18.9189 | 93.3333
28 | 2024-09-25 | 2024-10-02 | 0 |  | 100 | 0 | 70 | There is an engineer in the team took one day off, besides that there was a ticket with high complexity which caused the engineer to spend more time for the implementation.
29 | 2024-10-02 | 2024-10-09 | 0.38462 | 0 | 100 | 1.5385 | 95.4545
30 | 2024-10-09 | 2024-10-16 | 0.003125 | 0 | 100 | 37.5 | 88.2353 | In this sprint, 2 tasks have the actual point higher than the estimated point: - The first one is a task for implementing the UI of the new feature, during the implementation, the engineer raised some concerns about the UI and suggested some changes to improve it, therefore a rework has been conducted to adapt the specification improvement. - Another one is an engineer's task to support QA in executing some test cases. The task cost more time than estimated since the team raised some more abnormal cases to test, and also the data preparation phase took quite an amount of time.
31 | 2024-10-16 | 2024-10-23 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0!
32 | 2024-10-23 | 2024-10-30 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0!
33 | 2024-10-30 | 2024-11-06 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0!
34 | 2024-11-06 | 2024-11-13 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0!
35 | 2024-11-13 | 2024-11-20 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0!
36 | 2024-11-20 | 2024-11-27 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0!
37 | 2024-11-27 | 2024-12-04 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0!
38 | 2024-12-04 | 2024-12-11 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0!
39 | 2024-12-11 | 2024-12-18 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0!
40 | 2024-12-18 | 2024-12-25 | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0!
41 |  |  | #N/A |  | #N/A | #N/A | #N/A
42 |  |  | #N/A |  | #N/A | #N/A | #N/A
43 |  |  | #N/A |  | #N/A | #N/A | #N/A
44 |  |  | #N/A |  | #N/A | #N/A | #N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A

## 4.2 Project Summary_By Phase
|  | Project KPI Data | [5 empty] | No: BM-QT-1706-01
Version: 1.6
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD | [7 empty] | ISO/IEC 27001:2013&ISO 9001:2015
Phase | Sprint/ Week | Start date | End date | QA Bug Proportion (Q1) #/Mh Internal Bug Count / Total Actual Effort [MH] | UAT Bug Rate (Q2)% ( UAT Bug Count/ All Bug Count ) * 100 | Estimation Accuracy Rate (C1)% ( Total Actual Effort / Total Estimated Effort ) * 100 | Bug Handling Cost Rate (C2)% ( Total Bug Handling Effort / Total Actual Effort ) * 100 | Issue Closed Ratio (M1)% (Closed Issue Count / All Issue Count)*100 | Note
1 | 1 | 2024-03-07 | 2024-03-13 | 0 | #NUM! | 100 | 0 | 70
2 | 2 | 2024-03-14 | 2024-05-29 | 12.5502 | 10.7143 | 97.2656 | 47.8916 | 95.977
3
4
5
6
7
8
9
10
11
3 | 12 | 2024-05-29 | 2024-08-28 | 3.8232 | 0 | 103.3333 | 6.4516 | 96.8254
13
14
15
16
17
18
19
20
21
22
23
4 | 24 | 2024-08-28 | 2024-10-23 | 11.8823 | 0 | 98.2007 | 15.3248 | 85.7143
25
26
27
28
29
30
31
5 | 32 | 2024-10-23 | 2024-12-25 | #NUM! | #NUM! | #NUM! | #NUM! | #NUM!
33
34
35
36
37
38
39
40

## 5.1 Chart_By Sprint
| Project KPI Data |  |  | No: BM-QT-1706-01
Version: 1.6
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD |  |  |  | ISO/IEC 27001:2013&ISO 9001:2015
| UCL | Target | LCL
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| UCL | Target | LCL
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| UCL | Target | LCL
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| UCL | Target | LCL
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| UCL | Target | LCL
| 5 | 0 | -15
| 5 | 0 | -15
| 5 | 0 | -15
| 5 | 0 | -15
| 5 | 0 | -15
| 5 | 0 | -15
| 5 | 0 | -15
| 5 | 0 | -15
| 5 | 0 | -15
| 5 | 0 | -15
| 5 | 0 | -15
| 5 | 0 | -15
| 5 | 0 | -15
| 5 | 0 | -15
| 5 | 0 | -15
| 5 | 0 | -15
| 5 | 0 | -15
| 5 | 0 | -15
| 5 | 0 | -15
| UCL | Target | LCL
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90

## 5.2 Chart_By Phase
| Project KPI Data |  |  | No: BM-QT-1706-01
Version: 1.6
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD |  |  |  | ISO/IEC 27001:2013&ISO 9001:2015
| UCL | Target | LCL
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| 0.5 | 0.05 | 0
| UCL | Target | LCL
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| 20 | 5 | 0
| UCL | Target | LCL
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| 115 | 100 | 85
| UCL | Target | LCL
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| 20 | 10 | 5
| UCL | Target | LCL
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90
| 110 | 100 | 90

## 6. KPI analysis
|  | Project KPI Data |  |  |  |  | No: BM-QT-1706-01
Version: 1.6
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD | [6 empty] | ISO/IEC 27001:2013&ISO 9001:2015
Phase | Sprint/ Week | Start date | End date | Abnormal KPI | Target | Cause | Action of project | Follow up | Tracking result
| Total | 7