## History of changes
|  | TEST REPORT | No: BM-QT-1701-15
Version: 2.2
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD |  |  | ISO/IEC 27001:2013&ISO 9001:2015
HISTORY OF CHANGES
No | Change Item | Description of changes | Change Date
1 |  | Update format | 2021-05-04
2 | All sheet | Update mã biểu mẫu theo tiêu chuẩn ISO. | 22/09/2026

## Overview
|  | TESTING PROGRESS MANAGEMENT |  |  |  | No: BM-QT-1701-15
Version: 2.2
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD | [5 empty] | ISO/IEC 27001:2013&ISO 9001:2015
| Project name | <Project name> |  | Creator | <Creator>
| Project code | <Project code> |  | Create date | <Create date>
| Version | <Version> |  | Last Update | <Last Update>
VERSION HISTORY
| Version # | Action | Date | Description | Updated person | Note
| <0.1> | <Create new> | <YYYY/MM/DD> | <A brief description of the changed content> | <Updated person name> | <Other note if have>
| <0.2> | <Modified> | <YYYY/MM/DD> | <A brief description of the changed content> | <Updated person name> | <Other note if have>

## Task List & Plan
|  |  |  | TEST REPORT | [11 empty] | No: BM-QT-1701-15
Version: 2.2
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD | [15 empty] | ISO/IEC 27001:2013&ISO 9001:2015
Task List & Plan
| Creator | <Creator>
| Create date | <YYYY/MM/DD>
| [Test Environment] | [<Chrome/IE 8...>]
Note:
1. In case you have a column that all cells of it have the same value, you can summary it to create an related item in “Summary” area and delete related column. For example: Test Environment for all function is Chrome/IE 8 => you can create item as cell B6 and delete “Test environment” column
2. (*) is required field.
#ID(*) | Task List (*) | Type of Testing |  |  |  |  | Create test cases plan (*) |  |  | Execute test plan (*) |  |  | Bug plan | Start date (*) | End date (*) | Other |  |  |  | [Test Environment]
|  | UT | IT (*) | ST | AT | … | Number of Tcs | Effort (days) | Person Incharge | Number of Tcs | Effort (days) | Person Incharge |  |  |  | Criteria to start | Criteria to Finish | Criteria to Cancel/Stop test | …
1 | <Task 1> |  | ◯ | ◯ |  |  | 100 | 1.67 | <Creator> | 120 | 1.71 | <Executors> | 4 | <YYYY/MM/DD> | <YYYY/MM/DD> | <Main operation of Login and registration function is finished.> <Task 1 must be finish 100%> | <+ 100% test case is execute + All bugs are fixed and re-test + All of not fixed bugs/ pending items have been logged to agreed resolution document. …>. | <+ Dev has not performed Unit test yet. + Actual number of bugs is larger than plan.> |  | <Chrome/IE 8...>
2 | <Task 2> |  | ◯ |  |  |  | 80 | 1.33 | <Creator> | 96 | 1.37 | <Executors> | 3 | <YYYY/MM/DD> | <YYYY/MM/DD> | N/A | … | … |  | …
3 | <Task 3> | ◯ | ◯ | ◯ |  |  | 140 | 2.33 | <Creator> | 168 | 2.4 | <Executors> | 5 | <YYYY/MM/DD> | <YYYY/MM/DD> | <Main operation of Login and registration function is finished.> | … | … |  | …
4 | <Task 4> |  | ◯ |  |  |  | 95 | 1.58 | <Creator> | 114 | 1.63 | <Executors> | 3 | <YYYY/MM/DD> | <YYYY/MM/DD>
5 | <Task 5> |  | ◯ | ◯ |  |  | 70 | 1.17 | <Creator> | 84 | 1.2 | <Executors> | 3 | <YYYY/MM/DD> | <YYYY/MM/DD> | <Task 1 must be finish 100%>
6 | <Task 6> |  | ◯ |  |  |  | 155 | 2.58 | <Creator> | 186 | 2.66 | <Executors> | 6 | <YYYY/MM/DD> | <YYYY/MM/DD>
| Total | [5 empty] | 640 | 11 |  | 768 | 11 |  | 24

## Create Test case Progress
|  |  |  | TEST REPORT | [11 empty] | No: BM-QT-1701-15
Version: 2.2
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD | [15 empty] | ISO/IEC 27001:2013&ISO 9001:2015
Create test case
| Creator | <Creator>
| Create date | <YYYY/MM/DD>
| Start date | <YYYY/MM/DD>
| End date | <YYYY/MM/DD>
#ID(*) | Task List (*) | Person Incharge(*) | Created Number (*) |  |  | Progress (*) |  | Create date (*)
[8 empty] | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue
|  |  | Plan | Actual | Remain |  |  | 2015-11-12 | 2015-11-13 | 2015-11-14 | 2015-11-15 | 2015-11-16 | 2015-11-17 | 2015-11-18 | 2015-11-19 | 2015-11-20 | 2015-11-21 | 2015-11-22 | 2015-11-23 | 2015-11-24 | 2015-11-25 | 2015-11-26
1 | <Task 1> | <Creator> | 100 | 100 | 0 | 100% | Plan | 2015-11-12: 60; 2015-11-13: 40
[7 empty] | Actual | 2015-11-12: 75; 2015-11-13: 25
2 | <Task 2> | <Creator> | 140 | 80 | 60 | 57.14% | Plan | 2015-11-13: 20; 2015-11-14: 60
[7 empty] | Actual | 2015-11-13: 35; 2015-11-14: 45
3 | <Task 3> | <Creator> | 70 | 140 | -70 | 200% | Plan | 2015-11-15: 60; 2015-11-18: 60; 2015-11-19: 20
[7 empty] | Actual | 2015-11-14: 15; 2015-11-15: 60; 2015-11-18: 60; 2015-11-19: 5
4 | <Task 4> |  | 640 | 95 | 545 | 14.84% | Plan | 2015-11-19: 40; 2015-11-20: 55
[7 empty] | Actual | 2015-11-19: 55; 2015-11-20: 40
5 | <Task 6> |  |  | 20 | -20 | #DIV/0! | Plan | 2015-11-20: 5; 2015-11-21: 60; 2015-11-22: 5
[7 empty] | Actual | 2015-11-20: 20
6 |  |  |  | 0 | 0 | #DIV/0! | Plan | 2015-11-22: 55; 2015-11-25: 60; 2015-11-26: 40
Actual
| Total |  | 950 | 435 | 515 | 45.79%

## Execute Test Progress
|  |  |  | TEST REPORT | [11 empty] | No: BM-QT-1701-15
Version: 2.2
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD | [15 empty] | ISO/IEC 27001:2013&ISO 9001:2015
Execute testing
| Creator | <Creator>
| Create date | <YYYY/MM/DD>
| Start date | <YYYY/MM/DD>
| End date | <YYYY/MM/DD>
#ID(*) | Task List (*) | Person Incharge(*) | Execute Number (*) |  |  | Progress (*) |  | Execute date (*)
[8 empty] | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue
|  |  | Plan | Actual | Remain |  |  | 2015-11-12 | 2015-11-13 | 2015-11-14 | 2015-11-15 | 2015-11-16 | 2015-11-17 | 2015-11-18 | 2015-11-19 | 2015-11-20 | 2015-11-21 | 2015-11-22 | 2015-11-23 | 2015-11-24 | 2015-11-25 | 2015-11-26
1 | <Task 1> | <Creator> | 120 | 120 | 0 | 100% | Plan | 2015-11-12: 70; 2015-11-13: 50
[7 empty] | Actual | 2015-11-12: 75; 2015-11-13: 45
2 | <Task 3> | <Creator> | 168 | 96 | 72 | 57.14% | Plan | 2015-11-13: 20; 2015-11-14: 70; 2015-11-15: 6
[7 empty] | Actual | 2015-11-13: 25; 2015-11-14: 71
3 | <Task 5> | <Creator> | 84 | 168 | -84 | 200% | Plan | 2015-11-15: 64; 2015-11-18: 70; 2015-11-19: 34
[7 empty] | Actual | 2015-11-15: 70; 2015-11-18: 70; 2015-11-19: 28
4 | Total |  | 768 | 40 | 728 | 5.208% | Plan | 2015-11-19: 36; 2015-11-20: 70; 2015-11-21: 8
[7 empty] | Actual | 2015-11-19: 40
5 |  |  |  | 0 | 0 | #DIV/0! | Plan | 2015-11-21: 62; 2015-11-22: 22
Actual
6 |  |  |  | 0 | 0 | #DIV/0! | Plan | 2015-11-22: 48; 2015-11-25: 70; 2015-11-26: 68
Actual
| Total |  | 1140 | 424 | 716 | 37.19% | Delay | -5 | -5 | -6 | -6 | -6 | -6 | -6 | -4 | 66 | 136 | 206 | 206 | 206 | 276 | 344