## History of changes
|  | RELEASE NOTE | No: BM-QT-1701-18
Version: 1.4
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD |  |  | ISO/IEC 27001:2013&ISO 9001:2015
HISTORY OF CHANGES
No | Change Item | Description of changes | Change Date
1 |  | Add new | 2021-09-03
2 | Sheet Release Checklist, row 46 | Bổ sung item check "Review các risk liên quan đến hoạt động release" | 19/01/2022
3 | Sheet [Blockchain Project] Process for deploy to mainnet | Bổ sung Release Process để deploy lên mainnet dành cho dòng dự án Blockchain | 13/02/2023
4 | Sheet Release Process Sheet [Sampe]Release Process Sheet Infrastructure Checklist | Bổ sung Release Process để dành cho những dự án liên quan đến Infra trong hoạt động Release. Thêm mới sheet Infrastructure Checklist. | 2025-03-01
5 | All sheet | Update mã biểu mẫu theo tiêu chuẩn ISO. | 22/09/2026

## SampleRelease Process
|  | RELEASE NOTE |  |  | No: BM-QT-1701-18
Version: 1.4
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD |  |  |  |  | ISO/IEC 27001:2013&ISO 9001:2015
* Mandatory items
Release Date* |  | 2020-09-17
Expected start time |  | 8:00 2020-09-17
Expected end time |  | 16:00 2020-09-17
PIC (Person In Charge) |  | Nguyen Van A
Milestone/Sprint |  | 1.0 | Version | v.1.0.0
Environment |  | Staging/Production
Release Schedule*
Time |  | PIC | Task |  |  | Status
8:00 GMT 9/9/2020 |  | Sun* | Deploy API |  |  | FALSE
9:00 GMT 9/9/2020 |  | Sun* | Deploy Staging |  |  | FALSE
10:00 GMT 9/9/2020 |  | Client | Verify on Staging |  |  | FALSE
15:00 GMT 9/9/2020 |  | Sun* | Deploy on Production |  |  | FALSE
17:00 GMT 9/9/2020 |  | Client | Verify on Production |  |  | FALSE
....... | [5 empty] | FALSE
Target Release List*
Feature name |  | Redmine link |  | Testcase list |  | Test Result by [Sun* PIC Name]
Feature name 1 |  | https://dev.sun-asterisk.com/projects/abc/123 |  | Link TC (from case n to case m) |  | FALSE
Feature name 2 |  | https://dev.sun-asterisk.com/projects/abc/123 |  | Link TC (from case n to case m) |  | FALSE
Feature name 3 |  | https://dev.sun-asterisk.com/projects/abc/123 |  | Link TC (from case n to case m) |  | FALSE
Feature name 4 |  | https://dev.sun-asterisk.com/projects/abc/123 |  | Link TC (from case n to case m) |  | FALSE
Feature name 5 |  | https://dev.sun-asterisk.com/projects/abc/123 |  | Link TC (from case n to case m) |  | FALSE
........ |  | .... |  |  |  | FALSE
Infrastructure Release Note Link
Does this release require infrastructure configuration checking and/or infrastructure configuration changes? If "Yes", please use the Infrastructure checklist to re-evaluate the release environment. |  | Yes
Link checklist |  | Infrastructure Checklist
Confirm |  | FALSE
Sun* Final Inspection
PIC Name
Link checklist |  | https://dev.sun-asterisk.com/projects/abc/123
Confirm |  | TRUE
Remaining Items *
Description |  | Redmine link
Issue 1 |  | https://dev.sun-asterisk.com/projects/abc/123
Bug 1 |  | https://dev.sun-asterisk.com/projects/abc/123
...... |  | https://dev.sun-asterisk.com/projects/abc/123
Notes For Client (if have)
No. | Description
1 | System downtime/need maintain...
...... | .....
Client Acceptance Testcase List
No. | Function Name |  |  | Status
1 | Test feature Login |  |  | FALSE
2 | Test feature Sort |  |  | FALSE
3 | Test Order flow |  |  | FALSE
.... | ........... |  |  | FALSE
Approved List
Role |  | Name |  | Status
Client |  | Nguyen Van B |  | FALSE
Project leader |  | Nguyen Van C |  | FALSE
QA Leader |  | Nguyen Van D |  | FALSE
........ |  |  |  | FALSE
Release Process*
Note: All the operators have to follow the steps below while the operation proceeds. Especially do NOT carry out your operation until the previous step completed and confirmed.
# | Operator | Target (location where operation occur) | Operation | Estimated operation time (minutes) | Definition of Done | Done
Operation preparations
1 | SVN Nguyen Van A | Chatwork | Reports client to start release operation on the production environment. | 5 | Client confirm agreement about the plan | TRUE
2 | SVN Nguyen Van A | Chatwork | Confirm and notify all leader: client approves production operation starts | 5 |  | FALSE
3 | SVN Nguyen Van A SVN Nguyen Van B SVN Nguyen Van C | Chatwork, Meet | Confirm all feature will deploy. Check version of app and server. Version deploy: release_v1.2.0_20201112 Confirm release order : - Server - Native build - Frontend build | 5 |  | FALSE
4 | SVN Nguyen Van A SVN Nguyen Van B SVN Nguyen Van C | Chatwork, Meet | Update and confirm release checklist Update and confirm test scope (QA) | 15 |  | FALSE
Operation steps
5 | SVN Nguyen Van A | Teraform/ Codebuild | Update release tag for all repo. | 5 |  | FALSE
6 | SVN Nguyen Van A | CodePipeline | Deploy server (admin + API + worker) | 20 |  | FALSE
7 | SVN Nguyen Van A |  | Build ABC app | 10 |  | FALSE
| SVN Nguyen Van D | CodePipeline | Deploy ABC Web | 10 |  | FALSE
Check deployment logs, application logs
8 | SVN Nguyen Van A SVN Nguyen Van B SVN Nguyen Van C | Prod application | Confirm related feature from Server API and Native release success at the same version release. (Checklist commit, code) | 20 |  | FALSE
9 | SVN Nguyen Van A SVN Nguyen Van B SVN Nguyen Van C | Chatwork | Report To SVN Nguyen Van A deploy result SVN Nguyen Van A report To customer and confirm SVN QA test on application | 10 |  | FALSE
10 | SVN Nguyen Van A SVN Nguyen Van B SVN Nguyen Van C | Chatwork | Check application log after release if have any errors. | 5 |  | FALSE
Check run commands logs
11 | SVN Nguyen Van C | Chatwork | SVN Nguyen Van A reports SVN Nguyen Van B to start checking run command logs on prd-api 192.168.70.45 | 5
12 | SVN Nguyen Van C | prd-api 192.168.70.45 | SVN Nguyen Van A checks the run commands logs on prd-api 192.168.70.45 at folder /var/log/deploy/ | 10
13 | SVN Nguyen Van C | Chatwork | SVN Nguyen Van A reports SVN Nguyen Van B that the check run commands logs on prd-api 192.168.70.45 completed | 5
Check database changed, database logs
14 | SVN Nguyen Van C | Chatwork | SVN Nguyen Van A reports SVN Nguyen Van B to start checking database logs on prd-api 192.168.70.45 | 5
15 | SVN Nguyen Van C | prd-api 192.168.70.45 | SVN Nguyen Van A checks the database logs on prd-api 192.168.70.45 at folder /var/log/deploy/ | 10
16 | SVN Nguyen Van C | Chatwork | SVN Nguyen Van A reports SVN Nguyen Van B that the check database logs on prd-api 192.168.70.45 completed | 5
17 | SVN Nguyen Van A SVN Nguyen Van B SVN Nguyen Van C | Develop application | Hotfix bug if have any requirement from QA after confirming with clients. | 5 |  | FALSE
18 | SVN Nguyen Van A SVN Nguyen Van B SVN Nguyen Van C |  | Release hotfix with tag: release_v1.2.x_20201112 | 25 |  | FALSE
19 | SVN Nguyen Van C | Chatwork | Confirm bugs and all test cases pass. | 5 |  | FALSE
QA check after release
20 | SVN Nguyen Van C | Chatwork | SVN Nguyen Van A reports SVN Nguyen Van B the test cases will be executed to check after release | 10
21 | SVN Nguyen Van C | Chatwork | SVN Nguyen Van A reports SVN Nguyen Van B to start testing for deployed features on production environment | 5
22 | SVN Nguyen Van C | prd-web 192.168.70.35 prd-admin 192.168.70.55 | SVN Nguyen Van A executes the test for deployed features on production environment according to test plan | 25
23 | SVN Nguyen Van C | Chatwork | SVN Nguyen Van A reports SVN Nguyen Van B that the test for deployed features on production environment completed | 5
24 | SVN Nguyen Van A | Chatwork | SVN Nguyen Van A reports Customer that the test for deployed features on production environment completed | 5
Operation finish
25 | SVN Nguyen Van C | Chatwork | Report To clients deploy result | 5 |  | FALSE
26 | SVN Nguyen Van A SVN Nguyen Van B SVN Nguyen Van C | Chatwork | Update all report, deploy checklist | 5 |  | FALSE
Rollback Steps*
Note: All the operators have to follow the steps below while the operation proceeds. Especially do NOT carry out your operation until the previous step completed and confirmed.
# | Operator | Target (location where operation occur) | Operation | Estimated operation time (minutes) | Definition of Done | Done
Rollback preparations
1 | SVN Nguyen Van A | Chatwork | SVN Nguyen Van A reports client to start rollback operation on the production environment. | 5 |  | FALSE
2 | SVN Nguyen Van A | Chatwork | Confirm and notify all leader: client approves production rollback operation starts | 5 |  | FALSE
3 | SVN Nguyen Van A SVN Nguyen Van B SVN Nguyen Van C | Chatwork, Meet | Confirm all feature will change. Check version of app and server. Version rollback deploy: release_v1.2.0_20201112 Confirm release order : - Server - Native build (shipper app, Consumer app, Restaurant app) - Frontend build (Consumer web, Restaurant web) | 5 |  | FALSE
4 | SVN Nguyen Van A SVN Nguyen Van B SVN Nguyen Van C | Chatwork | Confirm database change to select rollback DB method - "rails db:rollback" - rollback rds from snapshots | 5 |  | FALSE
Rollback steps
5 | SVN Nguyen Van A | Chatwork | Apply method rollback. - "rails db:rollback" - rollback rds from snapshots | 40 |  | FALSE
6 | SVN Nguyen Van A | Terraform/ Codebuild | Update release tag for all repo. | 5 |  | FALSE
7 | SVN Nguyen Van A | CodePipeline | Deploy server (admin + API + worker) (Please describe all steps at here) | 20 |  | FALSE
8 | SVN Nguyen Van B |  | Build app | 10 |  | FALSE
9 | SVN Nguyen Van D | CodePipeline | Deploy App | 10 |  | FALSE
10 | SVN Nguyen Van A | CodePipeline | Deploy Web | 10 |  | FALSE
Check rollback logs, application logs
11 | SVN Nguyen Van A SVN Nguyen Van B SVN Nguyen Van C | Prod application | Confirm related feature from Server API and Native release success at the same version release. (Checklist commit, code) | 10 |  | FALSE
12 | SVN Nguyen Van A SVN Nguyen Van B SVN Nguyen Van C | Chatwork | Report To SVN Nguyen Van A deploy result SVN Nguyen Van A report To customer and confirm SVN QA test on application | 5 |  | FALSE
13 | SVN Nguyen Van A SVN Nguyen Van B SVN Nguyen Van C | Chatwork | Check application log after release if have any errors. | 5 |  | FALSE
Check database changed, database logs
14 | SVN Nguyen Van A SVN Nguyen Van B SVN Nguyen Van C | Prod application | SVN check migration on server. Check data in table changed if have. | 5 |  | FALSE
QA check after rollback
15 | SVN Nguyen Van B | Chatwork | Check with scope define release environment | 10 |  | FALSE
16 | SVN Nguyen Van A SVN Nguyen Van B SVN Nguyen Van C | Develop application | Hotfix bug if have any requirement from QA after confirming with clients. | 5 |  | FALSE
17 | SVN Nguyen Van A SVN Nguyen Van B SVN Nguyen Van C |  | Release hotfix with tag: release_v1.1.x_20201112 | 25 |  | FALSE
18 | SVN Nguyen Van B | Chatwork | Confirm bugs and all test cases pass. | 5 |  | FALSE
Rollback finish
19 | SVN Nguyen Van B | Chatwork | SVN Nguyen Van A reports client that rollback operation on the production environment have been finished | 5 |  | FALSE
20 | SVN Nguyen Van A SVN Nguyen Van B SVN Nguyen Van C | Chatwork | Update all report, deploy checklist | 5 |  | FALSE

## Release Checklist
|  | RELEASE NOTE |  |  |  |  | No: BM-QT-1701-18
Version: 1.4
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD | [6 empty] | ISO/IEC 27001:2013&ISO 9001:2015
Release Checklist
|  |  | Backend | Frontend | iOS | Android
PIC |  |  | Name | Name | Name | Name
Number of checked items |  |  | 0/28 | 0/16 | 0/28 | 0/24
# | Operation |  | Check Items |  |  |  | Note
Pre Release |  |  | Backend | Frontend | iOS | Android
1 | ■ Create a new pull request for this release. |  | FALSE | FALSE | FALSE | FALSE
2 | ■ Create a new tag for this release. |  | FALSE | FALSE | FALSE | FALSE
3 | ■ Check differences between a new tag and the last release tag. |  | FALSE | FALSE | FALSE | FALSE | Compare tag: git log --oneline previous_tag..new_tag --pretty=format:"%h %s - By '%an'"
4 | ■ Check the increase of the app version/build. |  | N/A | N/A | FALSE | FALSE
5 | ■ Check the target scheme for the corresponding environment and configuration file of this release. |  | N/A | N/A | FALSE | FALSE
6 | ■ Check the validity of the certificate and provisioning distribution. |  | N/A | N/A | FALSE | N/A | Certificate and provisioning distribution are provided by Apple in a year. Pls go to the Signing and Capabilities tab to check
7 | ■ Check the size information of the icon app. Refer: https://sal.vn/6zNgDb |  | N/A | N/A | FALSE | FALSE
8 | ■ Check the accuracy of deployment information. - Device type - Supported OS version - Device orientation |  | N/A | N/A | FALSE | N/A
9 | ■ Pass a review of all passcode statement for any DB change. |  | FALSE | N/A | FALSE | N/A
10 | ■ Check mapping between API Link, API Key on source code with API document. |  | N/A | FALSE | FALSE | N/A
11 | ■ Check the changes relating to the local database. |  | FALSE | N/A | FALSE | N/A
12 | ■ Check the changes of database model cause to a crash app or bugs. |  | FALSE | N/A | FALSE | N/A
13 | ■ Check the system has downtime or needs the maintenance mode. |  | FALSE | N/A | FALSE | N/A
14 | ■ Check the migrating old database model in case of database model has changed. |  | N/A | N/A | FALSE | FALSE | Migration List: db/migrate/20180531031337_change_columns_x.rb db/migrate/20180601011236_create_friendships.rb
15 | ■ Check the release dependencies between the platforms (Server, FE, IOS, Android) |  | FALSE | FALSE | FALSE | FALSE
16 | ■Has an environment variable preparation operation in case of updating or create a new environment variable |  | FALSE | FALSE | N/A | N/A
17 | ■ Check whether ABIs's correct with the application which's using Android NDK. |  | N/A | N/A | N/A | FALSE
18 | ■ Remove DEBUG and TEST LOG statement. |  | N/A | FALSE | FALSE | N/A
19 | ■ Check the right key for the environments (Google KEY, Third-party libs, ...) |  | N/A | N/A | FALSE | FALSE
20 | ■ Test whether file export exceeds the allowed capacity of Google Play? ■ Check the file extension if the application has any file handling feature. |  | N/A | N/A | N/A | FALSE
21 | ■ Check following Google's policy. |  | N/A | N/A | N/A | FALSE
22 | ■ Check MIN level SDK with the minimum supported version & MAX SDK with the maximum supported version on Android device. |  | N/A | N/A | N/A | FALSE
23 | ■ Update or create the environment variable in this release. |  | FALSE | N/A | N/A | N/A | Update: APP_VERSION = 2.01 New: SECRET_KEY = "AKIAMNEDNH67H"
24 | ■ Add or delete the setting file in this release. |  | FALSE | N/A | N/A | N/A | The setting files are google firebase, google purchase key.., saved on server. Depending on the function of each release, Dev need to determine the setting files. E.g.: google_firebase.json file, aws_keypair.pem file
25 | ■ Have any step to update in the admin |  | FALSE | N/A | N/A | N/A | Some functions are installed dynamically on the admin page, so it is necessary to define the update steps on admin before release. E.g.: Enable/Disable comment function, Change email to receive error messenger.
26 | ■ Add, edit or delete the batch/cronjob. |  | FALSE | N/A | N/A | N/A | Batch/Cronjob List: ●Add New: # 20 0 * * * sh $APP_HOME/config/batch_exec.sh Batches::BatchHandler.push_notification([1, 2, 3, 4]) 2>&1 ¦ logger -t batch_exec.s ●Update: n/a ●Delete: n/a
27 | ■ Mask email of the client in the staging environment and the production environment before the release. |  | FALSE | N/A | N/A | N/A | Mask email: Hide your real email, avoid being exposed to email, resulting in loss of personal information and spam mail.
28 | ■ List all scripts, rake tasks for this release. |  | FALSE | N/A | N/A | N/A | Script / rake task: ●Run before deploy: n/a ●Run after deploy: bundle exec rake task_a: update information bundle exec rake task_b: update information
29 | ■ Set Force Update Version if it needs. |  | N/A | N/A | FALSE | FALSE
30 | ■ Backup database |  | FALSE | N/A | N/A | N/A
31 | ■ Pass the review for all deploy commands. |  | FALSE | FALSE | FALSE | FALSE
32 | ■ Create a document for a server rollback when the deploy-process fails. |  | FALSE | N/A | N/A | N/A
33 | ■ Has a reporting process for the client about information before release (estimate time for the release, milestones for every step) |  | FALSE | FALSE | FALSE | FALSE
34 | ■ Review các risk liên quan đến hoạt động release (Risk Origin = Project Operation) |  | FALSE | FALSE | FALSE | FALSE
... | Add new item at here
Release |  |  | Backend | Frontend | iOS | Android
35 | ■ Confirm a report step at the beginning of the release. |  | FALSE | FALSE | FALSE | FALSE | Report contents: - Version release: - Release features (with ticket number): - Start time: - End time (estimated):
36 | ■ Inform the client & QA Team to conduct testing when the app's approved. ■ In case the app's rejected, report the client, then find the reason and fix it. |  | N/A | N/A | FALSE | FALSE
37 | ■ Recheck with the app having In-App purchase or redirect to Server from Google console |  | N/A | N/A | N/A | FALSE | - In-App purchase is a payment feature to buy products or service in the app - How to check: Check product_id of config in the app(product_id is a key config in google console and supplied by client) If the release doesn't have a payment feature, auto by pass this item.
38 | ■ Check the error during the deployment |  | FALSE | N/A | N/A | N/A | Error log: [ERROR] Can't found 'abc' library
39 | ■ Save the evidence of failed deployment Such as: - The screen shows the result (on terminal screen) - File text contains the result of deploy-progress |  | FALSE | N/A | N/A | N/A
... | .....
After Release |  |  | Backend | Frontend | iOS | Android
40 | ■ Has a reporting process at the finish of deployment |  | FALSE | FALSE | N/A | N/A | Report content: - Version release: - Release features (with ticket number): - Deployment is finished at: - Status: - Next action: check deploy result - Next action will finish at:
41 | ■ Check the status of service (database, puma, Redis, crontab) |  | FALSE | FALSE | FALSE | FALSE | ● Using "Final inspection checklist" of QA team
42 | ■ Check log of services (database, puma, Redis, crontab) |  | FALSE | FALSE | FALSE | N/A
43 | ■ Test on production environment via Test Plan E.g: - Google service - SMS service - ..... |  | FALSE | FALSE | FALSE | FALSE
44 | ■ Monitor the service conditions in the case the app has crashed or causes an error (Google Play Console reports, other tools integrated into the app, or user comments). |  | N/A | N/A | FALSE | FALSE
45 | ■ Has a reporting process when the release completed |  | FALSE | FALSE | FALSE | FALSE
... | ....

## Release Process
|  | RELEASE NOTE |  |  | No: BM-QT-1701-18
Version: 1.4
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD |  |  |  |  | ISO/IEC 27001:2013&ISO 9001:2015
* Mandatory items
Release Date* |  | YYYY/MM/DD
Expected start time
Expected end time
PIC (Person In Charge)
Milestone/Sprint |  |  | Version
Environment
Release Schedule*
Time |  | PIC | Task |  |  | Status
FALSE
FALSE
FALSE
....... | [5 empty] | FALSE
Target Release List*
Feature name |  | Redmine link |  | Testcase list |  | Test Result by [Sun* PIC Name]
FALSE
FALSE
FALSE
FALSE
FALSE
........ |  | .... |  |  |  | FALSE
Infrastructure Release Note Link
Does this release require infrastructure configuration checking and/or infrastructure configuration changes? If "Yes", please use the Infrastructure checklist to re-evaluate the release environment.
Link |  | Infrastructure Checklist
Confirm |  | FALSE
Sun* Final Inspection
PIC Name
Link checklist
Confirm |  | FALSE
Remaining Items *
Description |  | Redmine link
Issue 1
Bug 1
......
Notes For Client (if have)
No. | Description
1
...... | .....
Client Acceptance Testcase List
No. | Function Name |  |  | Status
1 | Test feature Login |  |  | FALSE
2 | Test feature Sort |  |  | FALSE
3 | Test Order flow |  |  | FALSE
.... | ........... |  |  | FALSE
Approved List
Role |  | Name |  | Status
Client |  | Nguyen Van B |  | FALSE
Project leader |  | Nguyen Van C |  | FALSE
QA Leader |  | Nguyen Van D |  | FALSE
........ |  |  |  | FALSE
Release Process*
Note: All the operators have to follow the steps below while the operation proceeds. Especially do NOT carry out your operation until the previous step completed and confirmed.
# | Operator | Target (location where operation occur) | Operation | Estimated operation time (minutes) | Definition of Done | Done
Operation preparations
FALSE
FALSE
FALSE
FALSE
Operation steps
FALSE
FALSE
FALSE
FALSE
Check deployment logs, application logs
FALSE
FALSE
FALSE
Check run commands logs
Check database changed, database logs
FALSE
FALSE
FALSE
QA check after release
Operation finish
FALSE
FALSE
Rollback Steps*
Note: All the operators have to follow the steps below while the operation proceeds. Especially do NOT carry out your operation until the previous step completed and confirmed.
# | Operator | Target (location where operation occur) | Operation | Estimated operation time (minutes) | Definition of Done | Done
Rollback preparations
TRUE
FALSE
FALSE
FALSE
Rollback steps
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Check rollback logs, application logs
FALSE
FALSE
FALSE
Check database changed, database logs
FALSE
QA check after rollback
FALSE
FALSE
FALSE
FALSE
Rollback finish
FALSE
FALSE

## Blockchain ProjectProcess for d
|  | Process for deploy to mainnet |  |  | No: BM-QT-1701-18
Version: 1.4
Issue Date: 22/09/2026
Deploy mainnet task
Categories | No. | Tasks | PIC | Status | Note | Updated Date
Deploy mainnet | 1 | Create a new wallet on an offline computer (without connecting Internet).
| 2 | Create and sign offline transaction and deploy smart contract by the offline wallet on the offline computer.
| 3 | Request native coin (ex: ETH/BTC/BNB, ...) -> native coin transferred to the offline wallet.
| 4 | Use another online computer (with connecting Internet) to broadcast offline transaction to deploy smart contract.
| 5 | Create and sign offline transaction to transfer ownership by the offline wallet on offline computer.
| 6 | Use another online computer to broadcast offline transaction for transfer ownership.
| 7 | Check balance of the offline wallet after executing the deploy smart contract and transferring ownership.
| 8 | Create and sign an offline refund native coin transaction by the offline wallet on the offline computer.
| 9 | Use another online computer to broadcast the offiline refund native coin transaction .

## Infrastructure Checklist
|  | RELEASE NOTE |  |  | No: BM-QT-1701-18
Version: 1.4
Issue Date: 22/09/2026
SUN ASTERISK VIETNAM CO., LTD |  |  |  |  | ISO/IEC 27001:2013&ISO 9001:2015
* Mandatory items
Release Date* |  | YYYY/MM/DD
Expected start time
Expected end time
PIC (Person In Charge)
Milestone/Sprint
Environment
Approved List
Role |  | Name |  | Status
Infra member |  |  |  | FALSE
Project Leader |  |  |  | FALSE
Infra Validation List*
No. | Risk Item | Description | Recommend | Level | Explain | How to setting | Done | Reason for not PASS
1 | AWS Root Account | When you first create an Amazon Web Services (AWS) account. This identity is called the AWS account root user and is accessed by signing in with the email address and password that you used to create the account. | → Create a new IAM User and grant Administrator permission → Don't create access keys for your AWS Root account | Very high | ● AWS strongly recommend that you do not use the root user for your everyday tasks, even the administrative ones. Instead, the best practice of using the root user only to create your first IAM user. ● The access key for your AWS account gives full access to all your resources for all AWS services, including your billing information | Creating Your First IAM Admin User and Group | FALSE
2 | AWS IAM | ■ AWS Architect | → IAM user creation is allowed/not allowed for each environment |  | ● Development environment: Admin, Infra, a few backend developers allowed to view logs ● Verification environment: Admin, Infra, Lead Backend allowed to read application logs ● Production environment: Admin, infra |  | FALSE
3 |  | ■ IAM User IAM User within AWS Root Account. Instead of sharing your root user credentials with others, you can create individual IAM users within AWS root account that correspond to users in your organization | → Create IAM User for each member → IAM user access keys are not shared. → Remove users who do not need access rights. Perform periodic checks (once a month). → The username of the IAM user is the email address. | High | AWS strongly discourage the use of shared user identities, where multiple entities share the same credentials. | Creating an IAM User in Your AWS Account | FALSE
4 |  | ■ IAM Group IAM groups are collections of IAM users in one AWS Root account. You can create IAM groups on a functional, organizational, or geographic basis, or by project | → Create IAM Group with Policy matching, and add IAM User to IAM Group For eample 1. Admin group 2. Infra group 3. FrontEnd Engnieer Group 4. BackEnd Engnieer Group 5. Native Engnieer Group Groups according to their responsibilities | High | You can provide each IAM group with permissions to access AWS resources by assigning one or more IAM policies. All policies assigned to an IAM group are inherited by the IAM users who are members of the group. | Creating IAM Groups | FALSE
|  | ■ IP address restriction role Create IP address restriction policies and attach them to each group. |  |  |  |  | FALSE
5 |  | ■ Access Key & Secret Key Access keys are used to digitally sign API calls made to AWS services. Each access key credential is comprised of an access key ID and a secret key. The secret key portion must be secured by the AWS account holder or the IAM user to whom they are assigned | → Should rotate their Access Keys on a regular basis (1 ~ 3 months) → Do not create Access Keys for your AWS Root account → Do not store Access Key on EC2 Instance → Use IAM Role when applications need access to AWS resources (view No.5) | High | ● The access key for your AWS account gives full access to all your resources for all AWS services, including your billing information ● In case of lost access key, hackers will use your access key to exploit the AWS resources | Creating, Modifying, and Viewing Access Keys | FALSE
6 |  | ■ As a rule, IAM user access keys are not used. All access within the AWS environment can be managed by IAM roles. | Cases where IAM user access keys are required 1. access via AWS CLI / SDK during development → Separate accounts for production and development environments 2. Access to AWS resources from external servers / management services → Minimise the permissions of the access keys provided and rotate them regularly. | High |  |  | FALSE
7 |  | ■ Multiple accounts Separate accounts for development, verification and production environments | Realisation example:. Use AWS Control Tower to Separate development, verification and production accounts | High |  |  | FALSE
8 | AWS IAM Role | Applications that run on an Amazon EC2 instance and that need access to AWS resources such as Amazon S3 buckets or an Amazon DynamoDB table must have security credentials in order to make programmatic requests to AWS. → Developers might distribute their credentials to each instance and applications can then use those credentials to access resources, but distributing long-term credentials to each instance is challenging to manage and a potential security risk. | → Use IAM Role when applications running on Amazon EC2 instances that need to access AWS resources Basically uses IAM roles rather than IAM users All access within the AWS environment can be managed by IAM roles Example. →If an application running on an Amazon EC2 instance needs access to an AWS resource, use an IAM role instead of an access key. →If Lambda needs DB credentials, store DB credentials in the Parameter Store, create a policy that allows access to the Parameter Store, and grant Lambda an IAM role to which the policy is applied. | Medium | Assuming the IAM Role returns temporary security credential and these have a configurable expiration and are automatically rotated. → It is means you don't always have to manage longterm credentials and IAM users for each entity that requires access to a resource | Working with IAM Roles | FALSE
9 | Password Policy | A password policy is a set of rules that define the type of password an IAM user can set | → Enable Password Policy → Rotate passwords | Very high | ● Set a minimum password length. ● Require specific character types, including uppercase letters, lowercase letters, numbers, and non-alphanumeric characters. Be sure to remind your users that passwords are case sensitive. ● Allow all IAM users to change their own passwords. | Setting a Password Policy | FALSE
10 | Enable Virtual MFA | ● A virtual MFA device uses a software application to generate a six-digit authentication code. The app can run on mobile hardware devices, including smartphones. ● You can enable only one MFA device per AWS account root user or IAM user, and the device can only be used by the specified user ● Create policy to enforce MFA for all groups. | → Enable a Virtual MFA Device for an IAM User → Enable a Virtual MFA Device for Your AWS Account Root User → Create Group of user then apply policy force enable MFA | Very high | Your password protects your account. You can also add a second layer of protection with 2-Step Verification by Virtual MFA | Enable a Virtual MFA Device | FALSE
11 | AWS Billing | It's a good idea to create a billing alarm to notify you if you exceed the limits of the budget | → Creating a Billing Alarm (You must be signed in using AWS root account) | Low | You can create billing alerts that notify you when your usage of your services exceeds thresholds that you define. When your usage exceeds these amounts, AWS sends you an email notification. | Create a Billing Alarm to Monitor Your Estimated AWS Charges | FALSE
12 | AWS Budget | With AWS Budgets, set custom budgets to track your costs and usage, and respond quickly to alerts received from email or SNS notifications if you exceed your threshold. | → Creating a Budget Alarm | Low | You can create budgets to track and take action on your costs and usage. You can also create budgets to track your aggregate Reserved Instance (RI) and Savings Plans utilization and coverage. By default, single accounts, the management account, and member accounts in an organization can create budgets | Create a Budget Alarm to Monitor Your Estimated AWS Charges | FALSE
15 | AWS EC2 Key Pair (OS_Lever) | ■ Managing OS-level Access to AWS EC2 Instance To access that instance using secure remote system access protocols, such as Secure Shell (SSH), or Windows Remote Desktop Protocol (RDP) | → Do not store Private Key on EC2 Instance | High | Amazon EC2 stores the public key only, and you store the private key. Anyone who possesses your private key can decrypt your login information, so it's important that you store your private keys in a secure place. | Creating a Key Pair | FALSE
16 |  | ■ Key Pairs for Multiple Users (OS_Lever) If you have several users that require access to a single instance, you can add user accounts to your instance. | → Create a key pair for each user, and add the public key information from each key pair to the .ssh/authorized_keys file for each user on your instance → Not have to distribute the same private key file that's used for the root account to multiple users. | Medium | ● Each Linux instance type launches with a default Linux system user account (Ex: Amazon Linux, the user name is ec2-user. For RHEL, the user name is ec2-user or root, ....) ● Using the default user account is adequate for many applications, but you may choose to add user accounts so that individuals can have their own files and workspaces. | Managing User Accounts on Your Linux Instance | FALSE
17 | Storing and Managing Encryption Keys | ■ AWS Key Management Service (KMS) It is a managed service that makes it easy for you to create and control the encryption keys used to encrypt your data. KMS is integrated with several other AWS services to help you protect the data you store with these services. | → Use AWS Key Management Service (KMS) | Low | Use AWS KMS to create and control the encryption keys used to encrypt your data | Creating a customer master key (CMK) | FALSE
18 |  | ■ KMS with Amazon S3 | → S3-Server-Side Encryption: Using SSE-KMS ● PUT/POST/COPY operation ● Initiate Multipart Upload | Low | Protect data at rest within Amazon S3 data centers by using AWS KMS. Amazon S3 now applies server-side encryption with Amazon S3 managed keys (SSE-S3) as the base level of encryption for every bucket in Amazon S3 | Server-Side Encryption with AWS KMS–Managed Keys | FALSE
19 |  | ■ KMS with Amazon EBS | → Uses AWS KMS to encrypt volumes and snapshots | Low | Data stored at rest on the volume, disk I/O, and snapshots created from the volume are all encrypted. The encryption occurs on the servers that host Amazon EC2 instances. | Creating an Amazon EBS Volume Encryption | FALSE
20 |  | ■ KMS with Amazon RDS | → Uses AWS KMS to encrypt the data stored on your Amazon RDS | Low | Data stored at rest on the volume, database snapshots, automated backups, and read replicas are all encrypted under the KMS CMK that you specified when you created the DB instance. | Enabling Amazon RDS Encryption for a DB Instance | FALSE
21 |  | ■ KMS with ElastiCache Redis | → Uses AWS KMS to encrypt the data stored on your Amazon ElastiCache | Low | Data stored at rest on the volume, database snapshots, automated backups, and read replicas are all encrypted under the KMS CMK that you specified when you created the DB instance. | Enabling Encryption for a ElastiCache Redis | FALSE
22 |  | ■ KMS with Amazon OpenSearch | → Uses AWS KMS to encrypt the data stored on your Amazon OpenSearch | Low | OpenSearch Service domains offer encryption of data at rest, a security feature that helps prevent unauthorized access to your data | Enabling Encryption for a OpenSearch Domain | FALSE
23 |  | ■ Preventing credential leakage Implement tools for credential prevention | → https://github.com/awslabs/git-secrets Developers use credential leakage prevention tools (deployed on personal PCs). Prevent accidental commits to local Git repositories → Check with Macie to see if it has been placed in S3. → GuardDuty functionality to detect and alert notification of unauthorised activity at instance level. | Option |  |  | FALSE
24 | Protecting Data at Rest | ■ On Amazon S3 Amazon S3 provides a number of security features for protection of data at rest | → Uses bucket-level or object-level permissions | Very high | Protect resources from unauthorized access and to prevent information disclosure, data integrity compromise, or deletion. | Bucket Policy Examples | FALSE
25 |  |  | → Enable Versioning | Medium | Amazon S3 supports object versions. Enable versioning to store a new version for every modified or deleted object from which you can restore compromised objects if necessary. | How Do I Enable or Suspend Versioning for an S3 Bucket | FALSE
26 |  |  | → Enable Replication | Low | Amazon S3 replicates each object across all Availability Zones within the respective region. Replication can provide data and service availability in the case of system failure. ● Same AWS Account ● Different AWS Accounts | How to Set Up Cross-Region Replication | FALSE
27 |  |  | → Use Encryption–client side | Low | Your applications encrypt data before submitting it to Amazon S3, and decrypt data after receiving it from Amazon S3. Data is stored in an encrypted form, with keys and algorithms only known to you ● Option 1: Using an AWS KMS–Managed Customer Master Key (CMK) ● Option 2: Using a Client-Side Master Key | Protecting Data Using Client-Side Encryption | FALSE
28 | Protect Data in Transit | ■ HTTP/HTTPS traffic By default, HTTP traffic is unprotected. SSL/TLS protection for HTTP traffic, also known as HTTPS | → Use HTTPS (HTTP over SSL/TLS) with server certificate authentication. | High | Offload HTTPS processing on Elastic Load Balancing to minimize impact on web servers while still protecting data in transit ● Listens on both the HTTP (80) and HTTPS (443) ports | Create a Application Load Balancer with an HTTPS Listener | FALSE
29 |  | ■ Remote Desktop Protocol (RDP) traffic Users who access Windows Terminal Services in the public cloud usually use the Microsoft Remote Desktop Protocol. By default, RDP connections establish an underlying SSL/TLS connection. | → Use Your Own X.509 Certificate | Negligible | For optimal protection, the Windows server being accessed should be issued a trusted X.509 certificate to protect from identity spoofing or manin-the-middle attacks. By default, Windows RDP servers use self-signed certificates, which are not trusted, and should be avoided. | - | FALSE
30 |  | ■ Secure Shell (SSH) traffic SSH is the preferred approach for establishing administrative connections to Linux servers. SSH is a protocol that, like SSL, provides a secure communications channel between the client and the server. | → Use SSH version 2 using non-privileged user accounts. | Negligible | SSH also supports tunneling, which you should use for running applications such as X-Windows on top of SSH, and protecting the application session in transit. | Connecting to Your Linux Instance from Windows Using PuTTY | FALSE
31 |  | ■ Database server traffic The most common protocol for encrypting data in transit is SSL/TLS, which stands for Secure Sockets Layer/Transport Layer Security. SSL/TLS creates a secure connection between a client and a server, and encrypts the data that is exchanged between them. | → Use SSL/TLS for data in transit | Low | Most modern databases support SSL/TLS wrappers for native database protocols. ● For database servers running on Amazon EC2, we recommend this approach to protecting data in transit. ● Amazon RDS provides support for SSL/TLS in some cases. (MySQL, MariaDB, Amazon Aurora, SQL Server, Oracle, or PostgreSQL) | Using SSL to Encrypt a Connection to a DB Instance | FALSE
32 | OS and Application | Secure Your Operating Systems and Applications | → Disable root API access keys and secret key | Very high | Do not create/uses Access key of AWS Root Account. (View No.1 & No.4) | - | FALSE
33 |  |  | → Restrict access to instances from limited IP ranges using Security Groups | High | A security group acts as a virtual firewall for your instance to control inbound and outbound traffic. The following are examples of the kinds of rules: ● Web server ● Database server ● Access from another instance in the same group ● Access from local computer ● Elastic Load Balancing (View No.29) | Security Group Rules Reference | FALSE
34 |  |  | → Using host-based firewalls to control access to each instance. | Low | Enable and add rule firewall of Windows Server or Linux. | - | FALSE
35 |  |  | → Password protect the .pem file on user machines | High | Protect .pem file safely, such as: ● Zip file with passwork option. ● Do not store .pem file on EC2 Instance | - | FALSE
36 |  |  | → Use bastion hosts to enforce control and visibility | High | Bastion hosts are instances that sit within your public subnet and are typically accessed using SSH or RDP, allowing you to use SSH or RDP to login to other instances within private subnets. | Quick Start Linux Bastion Hosts | FALSE
37 | Secure Your Infrastructure | ■ Amazon Virtual Private Cloud (VPC) With Amazon Virtual Private Cloud (VPC) you can create private clouds within the AWS public cloud. You need to establish IPSec tunnels are established between AWS and your infrastructure endpoints. | → IPSec over the Internet | Medium | Establish a private IPSec connection using IKEv1 and IPSec using standard AWS VPN facilities (Amazon VPC VPN gateways, customer gateways, and VPN connections). | Adding a Hardware Virtual Private Gateway to Your VPC | FALSE
38 |  | ■ AWS Network - Security groups Using security groups to manage access to instances that have similar functions and security requirements. | → Always use security groups & Only allow rule on demand | Very high | The following are examples of the kinds of rules: ● Web server ● Database server ● Access from another instance in the same group ● Access from local computer ● Elastic Load Balancing | Security Group Rules Reference | FALSE
39 |  | ■ AWS Network Access Control Lists Is an optional layer of security for your VPC that acts as a firewall for controlling traffic in and out of one or more subnets. | → Augment security groups with Network ACLs | Very high | NACLs are agnostic of TCP and UDP sessions, but they allow granular control over IP protocols, as well as control on a per-source/destination IP address and port for TCP and UDP. NACLs work in conjunction with security groups, and can allow or deny traffic even before it reaches the securitygroup. | Recommended Network ACL Rules for Your VPC | FALSE
40 |  | ■ AWS Trusted Advisor | -> Upgrade your Support package to Business, Enterprise On-Ramp, or Enterprise Support to unlock full features. | Low | Trusted Advisor inspects your AWS environment, and then makes recommendations when opportunities exist to save money, improve system availability and performance, or help close security gaps | Trusted Advisor Reference | FALSE
41 |  | ■ AWS Security Hub | -> Enable Security Hub in all supported AWS Regions. | Low | AWS Security Hub provides a consolidated view of your security status in AWS. Automate security checks, manage security findings, and identify the highest priority security issues across your AWS environment. | Security Hub Reference | FALSE
42 |  | ■ AWS Config | -> Enable rules related to utilized services such as EC2, ALB, etc. | Low | AWS Config provides a detailed view of the configuration of AWS resources in your AWS account. This includes how the resources are related to one another and how they were configured in the past so that you can see how the configurations and relationships change over time. | AWS Config Reference | FALSE
43 |  | ■ Amazon GuardDuty | -> Enable GuardDuty in all supported AWS Regions. | Low | Amazon GuardDuty is a threat detection service that continuously monitors your AWS accounts and workloads for malicious activity and delivers detailed security findings for visibility and remediation. | GuardDuty Reference | FALSE
44 |  | ■ AWS WAF Protect your service when expose to internet | Implementing AWS WAF. | High |  |  | FALSE
45 |  | ■ AWS Inspector | -> Enable AWS Inspector. | Low |  |  | FALSE
46 | Enable CloudTrail | AWS CloudTrail is an AWS service that helps you enable governance, compliance, and operational and risk auditing of your AWS account. | → Create CloudTrail & Apply to all Regions | Medium | ● Events include actions taken in the AWS Management Console, AWS Command Line Interface, and AWS SDKs and APIs. ● You can identify who or what took which action, what resources were acted upon, when the event occurred, and other details to help you analyze and respond to activity in your AWS account. | Creating a Trail | FALSE
47 | Logging | ■ Enable logging, as checking the logs allows you to see all current and historical information on communications, servers, services, users, etc. | CloudTrail logs | High |  |  | FALSE
|  |  | Route53 logs | Medium |  |  | FALSE
|  |  | AWS WAF logs | High |  |  | FALSE
|  |  | CloudFront logs | Low |  |  | FALSE
|  |  | S3 access logs | Medium |  |  | FALSE
|  |  | AWS API logs | High |  |  | FALSE
|  |  | ELB logs | Medium |  |  | FALSE
|  |  | Logs in VPC | Medium |  |  | FALSE
|  |  | Logs in OS / Middle Ware/ App | High |  |  | FALSE
48 | Secrets information management | Do not ""hold"" confidential information in files, but ""use"" information stored in secure areas. 1. Do not store confidential information on personal PCs or files, but use a secret information management service. Secret information is used from the secret management service. 2. Secret information is not stored in files, but only in the name of the administrator of the secret name. | Use Parameter Store; if not possible with Parameter Store, use Secrets Manager a: Cases where Parameter Store is used: - When you want to manage secret information and other parameters together. When you want to manage secret information and other parameters together. When you want to manage parameters in a hierarchical structure. b: Using the Secrets Manager: - When you want to use the secret rotation function. When you want to use the secret rotation function. When you want to control access using | Very high |  |  | FALSE
49 |  | ■ How to send a Secret In the Sun* environment 1. decide who is in charge of receiving the Secret from the customer 2. The person in charge creates a management file of who the secret was shared with. 3. the person in charge sends the Secret to the target person by DM 4. the Secret information itself is not left in the file, but is used in the Cloud's secure information management system In the customer's environment Have the Secret set in the Cloud's secure information management system on the customer's side. (Production environment) |  | Very high |  |  | FALSE